## Test Plan Fase 2 - Roas
TEST # | CATEGORY | TEST CRITERIA | RESULT | TEST DATE | OK / NOK | RE-TEST DATE | OK / NOK | NOTES
1. Local Connectivity
1.1 | Check US_Roas_CHI link health | Gi0/0.10: ping 10.2.10.1 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.2 |  | Gi0/0.20: ping 10.2.20.1 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.3 |  | Gi0/0.100: ping 10.2.100.1 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.4 |  | Gi0/0.200: ping 10.2.200.1 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.5 | Check US_Roas_NY link health | Gi0/0.10: ping 10.1.10.1 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.6 |  | Gi0/0.20: ping 10.1.20.1 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.7 |  | Gi0/0.100: ping 10.1.100.1 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.8 |  | Gi0/0.200: ping 10.1.200.1 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.9 | Test connectivity between CHI and NY PCs | ping from 10.2.10.10 to 10.1.10.10 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.10
2. Routing Tables
2.1 | Check static routes for US_Roas_CHI | "show ip route" | Static route for 10.1.0.0/16 via 172.16.1.10 | 2025-02-20 | OK
2.2 | Check static routes for US_Roas_NY | "show ip route" | Static route for 10.2.0.0/16 via 172.16.1.9 | 2025-02-20 | OK
2.3
3. Local Connectivity
3.1 | Locally connect to US_Roas_CHI | Connect laptop to device with console cable | able to connect via Putty | 2025-02-20 | OK
3.2 | Locally connect to US_Roas_NY | Connect laptop to device with console cable | able to connect via Putty | 2025-02-20 | OK
3.3 | Locally connect to US_AccessSW_CHI | Connect laptop to device with console cable | able to connect via Putty | 2025-02-20 | OK
3.4 | Locally connect to US_AccessSW_NY | Connect laptop to device with console cable | able to connect via Putty | 2025-02-20 | OK
3.5
4. VLAN Configuation
4.1 | Check VLAN config on US_AccessSW_CHI | "show vlan brief" | VLANs 10,20,100 and 200 in overview | 2025-02-20 | OK
4.2 | Check VLAN config on US_AccessSW_NY | "show vlan brief" | VLANs 10,20,100 and 200 in overview | 2025-02-20 | OK
4.3 | Check trunking on US_AccessSW_CHI | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed | 2025-02-20 | OK
4.4 | Check trunking on US_AccessSW_NY | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed | 2025-02-20 | OK
4.5 | Check subinterfaces on US_Roas_CHI | "show ip interface brief" | Subinterfaces for VLANs 10,20,100,200 are configures | 2025-02-20 | OK
4.6 | Check subinterfaces on US_Roas_NY | "show ip interface brief" | Subinterfaces for VLANs 10,20,100,200 are configures | 2025-02-20 | OK
4.7
5. Device and connection security
5.1 | VTY lines secured | "show running config" | password set and login required | 2025-02-20 | OK
5.2 | Unused ports disabled | "show interface status" | unused ports "disabled" | 2025-02-20 | OK
5.3 | Username and password set | Connect laptop to device with console cable | Prompt for username and password | 2025-02-20 | OK
5.4
6. SSH Testing between devices
6.1 | US_Access_SW_CHI → US_Roas_CHI | ssh -l admin 10.2.100.1 | able to connect via SSH after providing credentials | 2025-02-25 | OK
6.2 | US_Roas_CHI → US_Roas_NY | ssh -l admin 10.1.100.1 | able to connect via SSH after providing credentials | 2025-02-25 | OK
6.3 | US_Roas_NY → US_AccessSW_NY | ssh -l admin 10.1.100.10 | able to connect via SSH after providing credentials | 2025-02-25 | OK
6.4
7.
7.1
7.2
7.3

## Test Plan Fase 3 - Collaps_Core
TEST # | CATEGORY | TEST CRITERIA | RESULT | TEST DATE | OK / NOK | RE-TEST DATE | OK / NOK | NOTES
1. Local Connectivity
1.1 | Check EU_CoreSW1 link health | VLAN10_SVI: ping 10.3.10.3 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.2 |  | VLAN20_SVI: ping 10.3.20.3 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.3 |  | VLAN100_SVI: ping 10.3.100.3 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.4 |  | VLAN200_SVI: ping 10.3.200.3 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.5 | Check EU_CoreSW2 link health | VLAN10_SVI: ping 10.3.10.4 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.6 |  | VLAN20_SVI: ping 10.3.20.4 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.7 |  | VLAN100_SVI: ping 10.3.100.4 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.8 |  | VLAN200_SVI: ping 10.3.200.4 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.9 | Check EU_CoreSW - HSRP link healt | VLAN10: ping 10.3.10.5 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.10 |  | VLAN20: ping 10.3.20.5 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.11 |  | VLAN100: ping 10.3.100.5 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.12 |  | VLAN200: ping 10.3.200.5 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.13 | Check EU_AccessSW1 link health | ping 10.3.100.12 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.14 | Check EU_AccessSW2 link health | ping 10.3.100.13 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.15 | Test connectivity between BRU-PC01 and BRU-PC02 | ping from 10.3.10.10 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.16
2. Routing Tables
2.1 | Check static routes for EU_CoreSW1 | "show ip route" | All VLAN networks + subnet "connected" | 2025-03-05 | OK |  |  | All VLAN subnets are "connected" (C)
2.2 | Check static routes for EU_CoreSW2 | "show ip route" | All VLAN networks + subnet "connected" | 2025-03-05 | OK |  |  | All VLAN subnets are "connected" (C)
2.3
3. Local Connectivity
3.1 | Locally connect to EU_CoreSW1 | Connect laptop to device with console cable | able to connect via Putty | 2025-03-05 | OK
3.2 | Locally connect to EU_CoreSW2 | Connect laptop to device with console cable | able to connect via Putty | 2025-03-05 | OK
3.3 | Locally connect to EU_AccessSW1 | Connect laptop to device with console cable | able to connect via Putty | 2025-03-05 | OK
3.4 | Locally connect to EU_AccessSW2 | Connect laptop to device with console cable | able to connect via Putty | 2025-03-05 | OK
3.5
4. VLAN Configuation
4.1 | Check VLAN config on EU_AccessSW1 | "show vlan brief" | VLANs 10,20,100 and 200 + names in overview | 2025-03-05 | OK |  |  | VLANs defined
4.2 | Check VLAN config on EU_AccessSW2 | "show vlan brief" | VLANs 10,20,100 and 200 + names in overview | 2025-03-05 | OK |  |  | VLANs defined
4.3 | Check VLAN config on EU_CoreSW1 | "show vlan brief" | VLANs 10,20,100 and 200 + names in overview | 2025-03-05 | OK |  |  | VLANs defined
4.4 | Check VLAN config on EU_CoreSW2 | "show vlan brief" | VLANs 10,20,100 and 200 + names in overview | 2025-03-05 | OK |  |  | VLANs defined
4.5 | Check trunking on EU_AccessSW1 | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed on trunk interfaces | 2025-03-05 | OK |  |  | Allowed on Fa0/1, Fa0/2
4.6 | Check trunking on EU_AccessSW2 | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed on trunk interfaces | 2025-03-05 | OK |  |  | Allowed on Fa0/1, Fa0/2
4.7 | Check trunking on EU_CoreSW1 | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed on trunk interfaces | 2025-03-05 | OK |  |  | Allowed on Po1, Fa0/4, Fa0/5
4.8 | Check trunking on EU_CoreSW2 | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed on trunk interfaces | 2025-03-05 | OK |  |  | Allowed on Po1, Fa0/4, Fa0/5
4.9 | Check subinterfaces on EU_CoreSW1 | "show ip interface brief" | Subinterfaces for VLANs 10,20,100,200 are configures | 2025-03-05 | OK |  |  | SVIs defined
4.10 | Check subinterfaces on EU_CoreSW2 | "show ip interface brief" | Subinterfaces for VLANs 10,20,100,200 are configures | 2025-03-05 | OK |  |  | SVIs defined
4.11
5. Device and connection security
5.1 | VTY lines secured on EU_CoreSW1 | "show running-config" | password set and login required | 2025-03-05 | OK |  |  | CLI prompts credentials
5.2 | VTY lines secured on EU_CoreSW2 | "show running-config" | password set and login required | 2025-03-05 | OK |  |  | CLI prompts credentials
5.3 | VTY lines secured on EU_AccessSW1 | "show running-config" | password set and login required | 2025-03-05 | OK |  |  | CLI prompts credentials
5.4 | VTY lines secured on EU_AccessSW2 | "show running-config" | password set and login required | 2025-03-05 | OK |  |  | CLI prompts credentials
5.5 | Unused ports disabled on EU_CoreSW1 | "show interface status" | unused ports "disabled" | 2025-03-05 | OK
5.6 | Unused ports disabled on EU_CoreSW2 | "show interface status" | unused ports "disabled" | 2025-03-05 | OK
5.7 | Unused ports disabled on EU_AccessSW1 | "show interface status" | unused ports "disabled" | 2025-03-05 | OK
5.8 | Unused ports disabled on EU_AccessSW2 | "show interface status" | unused ports "disabled" | 2025-03-05 | OK
5.9 | Username and password set on EU_CoreSW1 | Connect to CLI (or via SSH) | Prompt for username and password | 2025-03-05 | OK
5.10 | Username and password set on EU_CoreSW2 | Connect to CLI (or via SSH) | Prompt for username and password | 2025-03-05 | OK
5.11 | Username and password set on EU_AccessSW1 | Connect to CLI (or via SSH) | Prompt for username and password | 2025-03-05 | OK
5.12 | Username and password set on EU_AccessSW2 | Connect to CLI (or via SSH) | Prompt for username and password | 2025-03-05 | OK
5.13 | Passwords encrypted in config files for EU_CoreSW1 | "show running-config" | Passwords encrypted + "service password encryption" | 2025-03-05 | OK
5.14 | Passwords encrypted in config files for EU_CoreSW2 | "show running-config" | Passwords encrypted + "service password encryption" | 2025-03-05 | OK
5.15 | Passwords encrypted in config files for EU_AccessSw1 | "show running-config" | Passwords encrypted + "service password encryption" | 2025-03-05 | OK
5.16 | Passwords encrypted in config files for EU_AccessSw2 | "show running-config" | Passwords encrypted + "service password encryption" | 2025-03-05 | OK
5.17
6. SSH Configuration
6.1 | EU_AccessSW1 → EU_AccessSW2 | ssh -l admin 10.3.100.13 | able to connect via via SSH, password prompted and access granted | 2025-03-05 | OK
6.2 | EU_CoreSW1 → EU_CoreSW2.vlan10 | ssh -l admin 10.3.10.4 | able to connect via via SSH, password prompted and access granted | 2025-03-05 | OK
6.3 | EU_AccessSW2 → EU_CoreSW1.vlan20 | ssh -l admin 10.3.20.3 | able to connect via via SSH, password prompted and access granted | 2025-03-05 | OK
6.4 | EU_CoreSW2 → EU_AccessSW1 | ssh -l admin 10.3.100.12 | able to connect via via SSH, password prompted and access granted | 2025-03-05 | OK
6.5
7. Spanning Tree Protocol
7.1 | Rapid-PVST enabled on EU_CoreSW1 | "show running-config" | "spanning-tree mode rapid-pvst" | 2025-03-05 | OK |  |  | Priority 0 - root bridge
7.2 | Rapid-PVST enabled on EU_CoreSW2 | "show running-config" | "spanning-tree mode rapid-pvst" | 2025-03-05 | OK |  |  | Priority 4096 - secondary root bridge
7.3 | Rapid-PVST enabled on EU_AccessSW1 | "show running-config" | "spanning-tree mode rapid-pvst" | 2025-03-05 | OK
7.4 | Rapid-PVST enabled on EU_AccessSW2 | "show running-config" | "spanning-tree mode rapid-pvst" | 2025-03-05 | OK
7.5 | Ensure path changes when link is broken | Disable link between EU_CoreSW1 and EU_AccessSW2 | Packet from BRU-PC01 to BRU-PC02 takes different route | 2025-03-05 | OK |  |  | Normal route: BRU-PC01 - EU_AccessSW1 - EU_CoreSW1 - EU_AccessSW2 - BRU-PC02 New route: BRU-PC01 - EU_AccessSW1 - EU_CoreSW1 - EU_CoreSW2 - EU_AccessSW2 - BRU-PC02
7.6 | BPDU Guard enabled on EU_CoreSW1 | "show running-config" | "spanning-tree portfast bpduguard default" | 2025-03-05 | OK
7.7 | BPDU Guard enabled on EU_CoreSW2 | "show running-config" | "spanning-tree portfast bpduguard default" | 2025-03-05 | OK
7.8 | BPDU Guard enabled on EU_AccessSW1 | "show running-config" | "spanning-tree portfast bpduguard default" | 2025-03-05 | OK
7.9 | BPDU Guard enabled on EU_AccessSW2 | "show running-config" | "spanning-tree portfast bpduguard default" | 2025-03-05 | OK
7.10
8. Etherchannel
8.1 | Etherchannel enabled on EU_CoreSW1 | "show running-config" | Interface Portchannel1 defined + interfaces Fa0/2 + Fa0/3 part of Po1 | 2025-03-05 | OK
8.2 | Etherchannel enabled on EU_CoreSW1 | "show running-config" | Interface Portchannel1 defined + interfaces Fa0/2 + Fa0/3 part of Po1 | 2025-03-05 | OK
8.3 | Etherchannel enabled on EU_CoreSW2 | "show etherchannel summary" | Po1 details + interfaces Fa0/2 + Fa0/3 in port-channel | 2025-03-05 | OK
8.4 | Etherchannel enabled on EU_CoreSW2 | "show etherchannel summary" | Po1 details + interfaces Fa0/2 + Fa0/3 in port-channel | 2025-03-05 | OK
8.5
9. Hot Standby Routing Protocol (HSRP)
9.1 | HSRP enabled on EU_CoreSW1 | "show standby" | "state is active" for all VLANs | 2025-03-05 | OK
9.2 | HSRP enabled on EU_CoreSW2 | "show standby" | "state is standby" for all VLANs | 2025-03-05 | OK
9.3

## Test Plan Fase 4 - Static_R (2)
TEST # | CATEGORY | TEST CRITERIA | RESULT | TEST DATE | OK / NOK | RE-TEST DATE | OK / NOK | NOTES
1. Local Connectivity
1.1 | Check US_FW_NY link health | ping 172.16.1.1 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.2 |  | ping 172.16.1.5 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.3 |  | ping 172.16.1.22 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.4 | Check EU_FW_BRU link health | ping 172.16.1.13 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.5 |  | ping 172.16.1.17 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.6 |  | ping 172.16.1.21 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.7 | Test connectivity between CHI-PC01 and BRU-PC02 | ping from 10.2.10.10 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.8 | Test connectivity between NY-PC01 and BRU-PC02 | ping from 10.1.10.10 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.9 | Test connectivity between CHI-PC01 and EU_FW_BRU | ping from 10.2.10.10 to 172.16.1.21 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.10 | Test connectivity between NY-PC01 and EU_FW_BRU | ping from 10.1.10.10 to 172.16.1.21 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.11 | Test connectivity between BRU-PC01 and US_FW_NY | ping from 10.3.10.10 to 172.16.1.22 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.12 | Test connectivity between BRU-PC02 and US_FW_NY | ping from 10.3.10.11 to 172.16.1.22 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.13
2. Routing Tables
2.1 | Check static routes for US_FW_NY | "show ip route" | All Point-to-Point networks and Last Resort "connected" | 2025-03-13 | OK |  |  | All Point-to-Point networks "connected" (C) and all static routes to the subnets "static" (S)
2.2 | Check static routes for EU_FW_BRU | "show ip route" | All Point-to-Point networks and Last Resort "connected" | 2025-03-13 | OK |  |  | All Point-to-Point networks "connected" (C) and all static routes to the subnets "static" (S)
2.3
3. Local Connectivity
3.1 | Locally connect to US_FW_NY | Connect laptop to device with console cable | able to connect via Putty | 2025-03-13 | OK
3.2 | Locally connect to EU_FW_BRU | Connect laptop to device with console cable | able to connect via Putty | 2025-03-13 | OK
3.3
4. Device and connection security
4.1 | VTY lines secured on US_FW_NY | "show running-config" | password set and login required | 2025-03-13 | OK
4.2 | VTY lines secured on EU_FW_BRU | "show running-config" | password set and login required | 2025-03-13 | OK
4.3 | Unused ports disabled on US_FW_NY | "show interface status" | unused ports "shutdown" | 2025-03-13 | OK
4.4 | Unused ports disabled on EU_FW_BRU | "show interface status" | unused ports "shutdown" | 2025-03-13 | OK
4.5 | Username and password set on US_FW_NY | Connect to CLI (or via SSH) | Prompt for username and password | 2025-03-13 | OK
4.6 | Username and password set on EU_FW_BRU | Connect to CLI (or via SSH) | Prompt for username and password | 2025-03-13 | OK
4.7 | Passwords encrypted in config files for US_FW_NY | "show running-config" | Passwords encrypted + "service password encryption" | 2025-03-13 | OK
4.8 | Passwords encrypted in config files for EU_FW_BRU | "show running-config" | Passwords encrypted + "service password encryption" | 2025-03-13 | OK
4.9
5. SSH Configuration
5.1 | EU_AccessSW1 → EU_FW_BRU | ssh -l admin 172.16.1.13 | able to connect via via SSH, password prompted and access granted | 2025-03-13 | OK
5.2 | EU_AccessSW2 → EU_FW_BRU | ssh -l admin 172.16.1.17 | able to connect via via SSH, password prompted and access granted | 2025-03-13 | OK
5.3 | US_AccessSW_CHI → US_FW_NY | ssh -l admin 172.16.1.5 | able to connect via via SSH, password prompted and access granted | 2025-03-13 | OK
5.4 | US_AccessSW_NY → US_FW_NY | ssh -l admin 172.16.1.1 | able to connect via via SSH, password prompted and access granted | 2025-03-13 | OK
5.5
6. US DHCP
7.1 | Connect device to Fa0/4 on US_AccessSW_CHI | ip address in range 10.2.10.0/26 | IP address 10.2.10.3, Gateway 10.2.10.1 | 2025-03-13 | OK
7.2 | Connect device to Fa0/5 on US_AccessSW_CHI | ip address in range 10.2.10.0/26 | IP address 10.2.10.2, Gateway 10.2.10.1 | 2025-03-13 | OK
7.3 | Connect device to Fa0/4 on US_AccessSW_NY | ip address in range 10.1.10.0/24 | IP address 10.1.10.3, Gateway 10.1.10.1 | 2025-03-13 | OK
7.4 | Connect device to Fa0/5 on US_AccessSW_NY | ip address in range 10.1.10.0/24 | IP address 10.1.10.2, Gateway 10.1.10.1 | 2025-03-13 | OK
7.5
7.6 | Ping from CHI-DHCP_1 to BRU-PC01 | ping from 10.2.10.2 to 10.3.10.10 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
7.7 | Ping from CHI-DHCP_2 to BRU-PC01 | ping from 10.2.10.3 to 10.3.10.10 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
7.8 | Ping from NY-DHCP_1 to BRU-PC02 | ping from 10.1.10.3 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
7.9 | Ping from NY-DHCP_2 to BRU-PC02 | ping from 10.1.10.2 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
7.10

## Test Plan Fase 5 - CentralDHCP
TEST # | CATEGORY | TEST CRITERIA | RESULT | TEST DATE | OK / NOK | RE-TEST DATE | OK / NOK | NOTES
1. EU CENTRAL DHCP
1.1 | Connect device to Fa0/7 on EU_AccessSW1 - DhcpTest2 | ip address in range 10.3.10.0/23 | IP address 10.3.10.7, Gateway 10.3.10.5 | 2025-03-14 | OK
1.2 | Connect device to Fa0/7 on EU_AccessSW2 - DhcpTest1 | ip address in range 10.3.10.0/23 | IP address 10.3.10.6, Gateway 10.3.10.5 | 2025-03-14 | OK
1.3
1.4 | Ping from DhcpTest1 to BRU-PC01 | ping from 10.2.10.6 to 10.3.10.10 | Ping statistics: 100% reply - 0% loss | 2025-03-14 | OK
1.5 | Ping from DhcpTest1 to CHI-PC01 | ping from 10.2.10.6 to 10.2.10.10 | Ping statistics: 100% reply - 0% loss | 2025-03-14 | OK
1.6 | Ping from DhcpTest1 to NY-PC01 | ping from 10.2.10.6 to 10.1.10.10 | Ping statistics: 100% reply - 0% loss | 2025-03-14 | OK
1.7 | Ping from DhcpTest2 to BRU-PC02 | ping from 10.2.10.7 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-14 | OK
1.8 | Ping from DhcpTest2 to CHI-PC01 | ping from 10.2.10.7 to 10.2.10.10 | Ping statistics: 100% reply - 0% loss | 2025-03-14 | OK
1.9 | Ping from DhcpTest2 to NY-PC01 | ping from 10.2.10.7 to 10.1.10.10 | Ping statistics: 100% reply - 0% loss | 2025-03-14 | OK
1.10

## Test Plan Fase 6 - OSPF LAN WAN
TEST # | CATEGORY | TEST CRITERIA | RESULT | TEST DATE | OK / NOK | RE-TEST DATE | OK / NOK | NOTES
1. OSPF CONFIGURATION
1.1 | Check OSPF configuration on US_FW_NY | "Show running-config" | Interface Gig0/0 - ip ospf network point-to-point | 2025-03-20 | OK
1.2 |  |  | Interface Gig0/1 - ip ospf network point-to-point | 2025-03-20 | OK
1.3 |  |  | Interface Gig0/2 - ip ospf network point-to-point | 2025-03-20 | OK
1.4 |  |  | Router ospf 10 - network 172.16.1.1 0.0.0.0 araea 0 | 2025-03-20 | OK
1.5 |  |  | Router ospf 10 - network 172.16.1.5 0.0.0.0 araea 0 | 2025-03-20 | OK
1.6 |  |  | Router ospf 10 - network 172.16.1.22 0.0.0.0 araea 0 | 2025-03-20 | OK
1.7 | Check OSPF configuration on US_Roas_CHI | "Show running-config" | Interface Gig0/1 - ip ospf network point-to-point | 2025-03-20 | OK
1.8 |  |  | Interface Gig0/2 - ip ospf network point-to-point | 2025-03-20 | OK
1.9 |  |  | Router ospf 10 - network 172.16.1.6 0.0.0.0 area 0 | 2025-03-20 | OK
1.10 |  |  | Router ospf 10 - network 172.16.1.9 0.0.0.0 area 0 | 2025-03-20 | OK
1.11 |  |  | Router ospf 10 - network 10.2.10.1 0.0.0.0 area 0 | 2025-03-20 | OK
1.12 |  |  | Router ospf 10 - network 10.2.20.1 0.0.0.0 area 0 | 2025-03-20 | OK
1.13 |  |  | Router ospf 10 - network 10.2.100.1 0.0.0.0 area 0 | 2025-03-20 | OK
1.14 |  |  | Router ospf 10 - network 10.2.200.1 0.0.0.0 area 0 | 2025-03-20 | OK
1.15 | Check OSPF configuration on US_Roas_CHI | "Show running-config" | Interface Gig0/1 - ip ospf network point-to-point | 2025-03-20 | OK
1.16 |  |  | Interface Gig0/2 - ip ospf network point-to-point | 2025-03-20 | OK
1.17 |  |  | Router ospf 10 - network 172.16.1.2 0.0.0.0 area 0 | 2025-03-20 | OK
1.18 |  |  | Router ospf 10 - network 172.16.1.10 0.0.0.0 area 0 | 2025-03-20 | OK
1.19 |  |  | Router ospf 10 - network 10.1.10.1 0.0.0.0 area 0 | 2025-03-20 | OK
1.20 |  |  | Router ospf 10 - network 10.1.20.1 0.0.0.0 area 0 | 2025-03-20 | OK
1.21 |  |  | Router ospf 10 - network 10.1.100.1 0.0.0.0 area 0 | 2025-03-20 | OK
1.22 |  |  | Router ospf 10 - network 10.1.200.1 0.0.0.0 area 0 | 2025-03-20 | OK
1.23 | Check OSPF configuration on EU_FW_BRU | "Show running-config" | Interface Gig0/0 - ip ospf network point-to-point | 2025-03-20 | OK
1.24 |  |  | Interface Gig0/1 - ip ospf network point-to-point | 2025-03-20 | OK
1.25 |  |  | Interface Gig0/2 - ip ospf network point-to-point | 2025-03-20 | OK
1.26 |  |  | Router ospf 10 - network 172.16.1.13 0.0.0.0 area 0 | 2025-03-20 | OK
1.27 |  |  | Router ospf 10 - network 172.16.1.17 0.0.0.0 area 0 | 2025-03-20 | OK
1.28 |  |  | Router ospf 10 - network 172.16.1.21 0.0.0.0 area 0 | 2025-03-20 | OK
1.29 | Check OSPF configuration on EU_CoreSW1 | "Show running-config" | Interface Fa0/1 - ip ospf network point-to-point | 2025-03-20 | OK
1.30 |  |  | Router ospf 10 - passive-interface Fa0/2 | 2025-03-20 | OK
1.31 |  |  | Router ospf 10 - passive-interface Fa0/3 | 2025-03-20 | OK
1.32 |  |  | Router ospf 10 - passive-interface Fa0/4 | 2025-03-20 | OK
1.33 |  |  | Router ospf 10 - passive-interface Fa0/5 | 2025-03-20 | OK
1.34 |  |  | Router ospf 10 - network 172.16.1.14 0.0.0.0 area 0 | 2025-03-20 | OK
1.35 |  |  | Router ospf 10 - network 10.3.10.3 0.0.0.0 area 0 | 2025-03-20 | OK
1.36 |  |  | Router ospf 10 - network 10.3.20.3 0.0.0.0 area 0 | 2025-03-20 | OK
1.37 |  |  | Router ospf 10 - network 10.3.100.3 0.0.0.0 area 0 | 2025-03-20 | OK
1.38 |  |  | Router ospf 10 - network 10.3.200.3 0.0.0.0 area 0 | 2025-03-20 | OK
1.39 | Check OSPF configuration on EU_CoreSW2 | "Show running-config" | Interface Fa0/1 - ip ospf network point-to-point | 2025-03-20 | OK
1.40 |  |  | Router ospf 10 - passive-interface Fa0/2 | 2025-03-20 | OK
1.41 |  |  | Router ospf 10 - passive-interface Fa0/3 | 2025-03-20 | OK
1.42 |  |  | Router ospf 10 - passive-interface Fa0/4 | 2025-03-20 | OK
1.43 |  |  | Router ospf 10 - passive-interface Fa0/5 | 2025-03-20 | OK
1.44 |  |  | Router ospf 10 - network 172.16.1.18 0.0.0.0 area 0 | 2025-03-20 | OK
1.45 |  |  | Router ospf 10 - network 10.3.10.4 0.0.0.0 area 0 | 2025-03-20 | OK
1.46 |  |  | Router ospf 10 - network 10.3.20.4 0.0.0.0 area 0 | 2025-03-20 | OK
1.47 |  |  | Router ospf 10 - network 10.3.100.4 0.0.0.0 area 0 | 2025-03-20 | OK
1.48 |  |  | Router ospf 10 - network 10.3.200.4 0.0.0.0 area 0 | 2025-03-20 | OK
2. OSPF NEIGHBOR RELATIONSHIPS
2.1 | Check OSPF neighbor for US_FW_NY | "show ip ospf neighbor" | Neighbor with EU_FW_BRU - Address 172.16.1.21 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/0
2.2 |  |  | Neighbor with US_Roas_NY - Address 172.16.1.2 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/1
2.3 |  |  | Neighbor with US_Roas_CHI - Address 172.16.1.6 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/2
2.4 | Check OSPF neighbor for US_Roas_NY | "show ip ospf neighbor" | Neighbor with US_FW_NY - Address 172.16.1.1 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/2
2.5 |  |  | Neighbor with US_Roas_CHI - Address 172.16.1.9 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/1
2.6 | Check OSPF neighbor for US_Roas_CHI | "show ip ospf neighbor" | Neighbor with US_FW_NY - Address 172.16.1.5 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/2
2.7 |  |  | Neighbor with US_Roas_NY - Address 172.16.1.10 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/1
2.8 | Check OSPF neighbor for EU_FW_BRU | "show ip ospf neighbor" | Neighbor with US_FW_NY - Address 172.16.1.22 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/0
2.9 |  |  | Neighbor with EU_CoreSW1 - Address 172.16.1.14 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/1
2.10 |  |  | Neighbor with EU_CoreSW2 - Address 172.16.1.18 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/2
2.11 | Check OSPF neighbor for EU_CoreSW1 | "show ip ospf neighbor" | Neighbor with EU_FW_BRU - Address 172.16.1.13 / State: FULL | 2025-03-20 | OK |  |  | On interface Fa0/1
2.12 |  |  | Neighbor with VLAN10 - Address 10.3.10.4 / State: FULL/DR | 2025-03-20 | OK |  |  | VLAN10
2.13 |  |  | Neighbor with VLAN20 - Address 10.3.20.4 / State: FULL/DR | 2025-03-20 | OK |  |  | VLAN20
2.14 |  |  | Neighbor with VLAN100 - Address 10.3.100.4 / State: FULL/DR | 2025-03-20 | OK |  |  | VLAN100
2.15 |  |  | Neighbor with VLAN200 - Address 10.3.200.4 / State: FULL/DR | 2025-03-20 | OK |  |  | VLAN200
2.16 | Check OSPF neighbor for EU_CoreSW2 | "show ip ospf neighbor" | Neighbor with EU_FW_BRU - Address 172.16.1.17 / State: FULL | 2025-03-20 | OK |  |  | On interface Fa0/1
2.17 |  |  | Neighbor with VLAN10 - Address 10.3.10.3 / State: FULL/BDR | 2025-03-20 | OK |  |  | VLAN10
2.18 |  |  | Neighbor with VLAN20 - Address 10.3.20.3 / State: FULL/BDR | 2025-03-20 | OK |  |  | VLAN20
2.19 |  |  | Neighbor with VLAN100 - Address 10.3.100.3 / State: FULL/BDR | 2025-03-20 | OK |  |  | VLAN100
2.20 |  |  | Neighbor with VLAN200 - Address 10.3.200.3 / State: FULL/BDR | 2025-03-20 | OK |  |  | VLAN200
3. OSPF ROUTES
3.1 | Check OSPF routes for US_FW_NY | "show ip route ospf" | All connected subnets marked with "O" (OSPF) | 2025-03-20 | OK
3.2 | Check OSPF routes for US_Roas-CHI | "show ip route ospf" | All connected subnets marked with "O" (OSPF) | 2025-03-20 | OK
3.3 | Check OSPF routes for US_Roas-NY | "show ip route ospf" | All connected subnets marked with "O" (OSPF) | 2025-03-20 | OK
3.4 | Check OSPF routes for EU_FW_BRU | "show ip route ospf" | All connected subnets marked with "O" (OSPF) | 2025-03-20 | OK
3.5 | Check OSPF routes for EU_CoreSW1 | "show ip route ospf" | All connected subnets marked with "O" (OSPF) | 2025-03-20 | OK
3.6 | Check OSPF routes for EU_CoreSW1 | "show ip route ospf" | All connected subnets marked with "O" (OSPF)
4. CHECK CONNECTIVITY
4.1 | Test connectivity between CHI-PC01 and BRU-PC02 | ping from 10.2.10.10 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK
4.2 | Test connectivity between NY-PC01 and BRU-PC02 | ping from 10.1.10.10 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK
4.3 | Test connectivity between CHI-PC01 and EU_FW_BRU | ping from 10.2.10.10 to 172.16.1.21 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK
4.4 | Test connectivity between NY-PC01 and EU_FW_BRU | ping from 10.1.10.10 to 172.16.1.21 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK
4.5 | Test connectivity between BRU-PC01 and US_FW_NY | ping from 10.3.10.10 to 172.16.1.22 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK
4.6 | Test connectivity between BRU-PC02 and US_FW_NY | ping from 10.3.10.11 to 172.16.1.22 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK

## Test Plan Fase 7 - WAN
TEST # | CATEGORY | TEST CRITERIA | RESULT | TEST DATE | OK / NOK | RE-TEST DATE | OK / NOK | NOTES
1. OSPF CONFIGURATION
1.1 | Check OSPF configuration on US_FW_NY | "Show running-config" | Interface Gig0/0 - ip ospf network point-to-point | 2025-03-20 | OK
1.2 |  |  | Interface Gig0/1 - ip ospf network point-to-point | 2025-03-20 | OK
1.3 |  |  | Interface Gig0/2 - ip ospf network point-to-point | 2025-03-20 | OK
1.4 |  |  | Router ospf 10 - network 172.16.1.1 0.0.0.0 araea 0 | 2025-03-20 | OK
1.5 |  |  | Router ospf 10 - network 172.16.1.5 0.0.0.0 araea 0 | 2025-03-20 | OK
1.6 |  |  | Router ospf 10 - network 23.12.56.13 0.0.0.0 araea 0 | 2025-03-20 | OK
1.7 | Check OSPF configuration on EU_FW_BRU | "Show running-config" | Interface Gig0/0 - ip ospf network point-to-point | 2025-03-20 | OK
1.8 |  |  | Interface Gig0/1 - ip ospf network point-to-point | 2025-03-20 | OK
1.9 |  |  | Interface Gig0/2 - ip ospf network point-to-point | 2025-03-20 | OK
1.10 |  |  | Router ospf 10 - network 172.16.1.13 0.0.0.0 area 0 | 2025-03-20 | OK
1.11 |  |  | Router ospf 10 - network 172.16.1.17 0.0.0.0 area 0 | 2025-03-20 | OK
1.12 |  |  | Router ospf 10 - network 195.13.1.221 0.0.0.0 area 0 | 2025-03-20 | OK
1.13 | Check OSPF configuration on R_PROVIDER | "Show running-config" | Interface Gig0/1 - ip ospf network point-to-point | 2025-03-20 | OK
1.14 |  |  | Interface Gig0/2 - ip ospf network point-to-point | 2025-03-20 | OK
1.15 |  |  | Router ospf 10 - network 23.12.56.14 0.0.0.0 area 0 | 2025-03-20 | OK
1.16 |  |  | Router ospf 10 - network 195.13.1.222 0.0.0.0 area 0 | 2025-03-20 | OK
2. OSPF NEIGHBOR RELATIONSHIPS
2.1 | Check OSPF neighbor for US_FW_NY | "show ip ospf neighbor" | Neighbor with R_PROVIDER - Address 23.12.56.14 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/0
2.2 |  |  | Neighbor with US_Roas_NY - Address 172.16.1.2 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/1
2.3 |  |  | Neighbor with US_Roas_CHI - Address 172.16.1.6 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/2
2.4 | Check OSPF neighbor for R_PROVIDER | "show ip ospf neighbor" | Neighbor with US_FW_NY - Address 23.12.56.13 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/1
2.5 |  |  | Neighbor with EU_FW_BRU - Address 195.13.1.221 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/2
2.6 | Check OSPF neighbor for EU_FW_BRU | "show ip ospf neighbor" | Neighbor with R_PROVIDER - Address 195.13.1.222 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/0
2.7 |  |  | Neighbor with EU_CoreSW1 - Address 172.16.1.14 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/1
2.8 |  |  | Neighbor with EU_CoreSW2 - Address 172.16.1.18 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/2
3. OSPF ROUTES
3.1 | Check OSPF routes for US_FW_NY | "show ip route ospf" | All connected subnets marked with "O" (OSPF) | 2025-03-20 | OK
3.2 | Check OSPF routes for EU_FW_BRU | "show ip route ospf" | All connected subnets marked with "O" (OSPF) | 2025-03-20 | OK
3.3 | Check OSPF routes for R_PROVIDER | "show ip route ospf" | All connected subnets marked with "O" (OSPF) | 2025-03-20 | OK
4. CHECK CONNECTIVITY
4.1 | Test connectivity between CHI-PC01 and BRU-PC02 | ping from 10.2.10.10 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK
4.2 | Test connectivity between NY-PC01 and BRU-PC02 | ping from 10.1.10.10 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK
4.3 | Test connectivity between CHI-PC01 and EU_FW_BRU | ping from 10.2.10.10 to 195.13.1.221 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK
4.4 | Test connectivity between NY-PC01 and EU_FW_BRU | ping from 10.1.10.10 to 195.13.1.221 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK
4.5 | Test connectivity between BRU-PC01 and US_FW_NY | ping from 10.3.10.10 to 23.12.56.13 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK
4.6 | Test connectivity between BRU-PC01 and US_FW_NY | ping from 10.3.10.11 to 23.12.56.13 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK
4.7 | Test connectivity between BRU-PC01 and R_PROVIDER | ping from 10.3.10.11 to 23.12.56.14 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK
4.8 | Test connectivity between NY-PC01 and R_PROVIDER | ping from 10.1.10.10 to 195.13.1.222 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK

## Test Plan Fase 8 - Monitoring
TEST # | CATEGORY | TEST CRITERIA | RESULT | TEST DATE | OK / NOK | RE-TEST DATE | OK / NOK | NOTES
1. NTP CONFIGURATION
1.1 | Check NTP configuration on US_AccessSW_CHI | "Show running-config" | ntp server 10.3.200.18 | 2025-03-27 | OK |  |  | Ensuring time stamp in Syslog is synchronised
1.2 | Check NTP configuration on US_AccessSW_NY | "Show running-config" | ntp server 10.3.200.18 | 2025-03-27 | OK |  |  | Ensuring time stamp in Syslog is synchronised
1.3 | Check NTP configuration on US_Roas_CHI | "Show running-config" | ntp server 10.3.200.18 | 2025-03-27 | OK |  |  | Ensuring time stamp in Syslog is synchronised
1.4 | Check NTP configuration on US_Roas_NY | "Show running-config" | ntp server 10.3.200.18 | 2025-03-27 | OK |  |  | Ensuring time stamp in Syslog is synchronised
1.5 | Check NTP configuration on US_FW_NY | "Show running-config" | ntp server 10.3.200.18 | 2025-03-27 | OK |  |  | Ensuring time stamp in Syslog is synchronised
1.6 | Check NTP configuration on EU_FW_BRU | "Show running-config" | ntp server 10.3.200.18 | 2025-03-27 | OK |  |  | Ensuring time stamp in Syslog is synchronised
1.7 | Check NTP configuration on EU_CoreSW1 | "Show running-config" | ntp server 10.3.200.18 | 2025-03-27 | OK |  |  | Ensuring time stamp in Syslog is synchronised
1.8 | Check NTP configuration on EU_CoreSW2 | "Show running-config" | ntp server 10.3.200.18 | 2025-03-27 | OK |  |  | Ensuring time stamp in Syslog is synchronised
1.9 | Check NTP configuration on EU_AccessSW1 | "Show running-config" | ntp server 10.3.200.18 | 2025-03-27 | OK |  |  | Ensuring time stamp in Syslog is synchronised
1.10 | Check NTP configuration on EU_AccessSW2 | "Show running-config" | ntp server 10.3.200.18 | 2025-03-27 | OK |  |  | Ensuring time stamp in Syslog is synchronised
2. SYSLOG CONFIGURATION
2.1 | Check logging configuration on US_AccessSW_CHI | "Show running-config" | logging 10.3.200.18 | 2025-03-27 | OK
2.2 | Check logging configuration on US_AccessSW_NY | "Show running-config" | logging 10.3.200.18 | 2025-03-27 | OK
2.3 | Check logging configuration on US_Roas_CHI | "Show running-config" | logging 10.3.200.18 | 2025-03-27 | OK
2.4 | Check logging configuration on US_Roas_NY | "Show running-config" | logging 10.3.200.18 | 2025-03-27 | OK
2.5 | Check logging configuration on US_FW_NY | "Show running-config" | logging 10.3.200.18 | 2025-03-27 | OK
2.6 | Check logging configuration on EU_FW_BRU | "Show running-config" | logging 10.3.200.18 | 2025-03-27 | OK
2.7 | Check logging configuration on EU_CoreSW1 | "Show running-config" | logging 10.3.200.18 | 2025-03-27 | OK
2.8 | Check logging configuration on EU_CoreSW2 | "Show running-config" | logging 10.3.200.18 | 2025-03-27 | OK
2.9 | Check logging configuration on EU_AccessSW1 | "Show running-config" | logging 10.3.200.18 | 2025-03-27 | OK
2.10 | Check logging configuration on EU_AccessSW2 | "Show running-config" | logging 10.3.200.18 | 2025-03-27 | OK
2.11 | Check NTP configuration on Monitoring Server | Monitoring server --> Services --> NTP | NTP Service ON | 2025-03-27 | OK
2.12 |  |  | Check date and time set to current date/time | 2025-03-27 | NOK | 2025-03-27 | OK | Whenever Packet Tracer is closed, this server is shut down and date/time paused
2.13 | Check logging output on Monitoring Server | Monitoring server --> Services --> SYSLOG | SYSLOG Service ON | 2025-03-27 | OK
2.14 |  |  | Log showing entries of network devices | 2025-03-27 | OK |  |  | E.g.: %HSRP-6-STATECHANGE: Vlan1° Grp 10 state Speak -> Standby
3. TFTP CONFIGURATION
3.1 | Manually back up running config of US_AccessSW_CHI to Monitoring server | "copy running-config tftp: --> 10.3.200.18 | Writing running-config…!! OK | 2025-03-27 | OK
3.2 | Manually back up running config of US_AccessSW_NY to Monitoring server | "copy running-config tftp: --> 10.3.200.18 | Writing running-config…!! OK | 2025-03-27 | OK
3.3 | Manually back up running config of US_Roas_CHI to Monitoring server | "copy running-config tftp: --> 10.3.200.18 | Writing running-config…!! OK | 2025-03-27 | OK
3.4 | Manually back up running config of US_Roas_NY to Monitoring server | "copy running-config tftp: --> 10.3.200.18 | Writing running-config…!! OK | 2025-03-27 | OK
3.5 | Manually back up running config of US_FW_NY to Monitoring server | "copy running-config tftp: --> 10.3.200.18 | Writing running-config…!! OK | 2025-03-27 | OK
3.6 | Manually back up running config of EU_FW_BRU to Monitoring server | "copy running-config tftp: --> 10.3.200.18 | Writing running-config…!! OK | 2025-03-27 | OK
3.7 | Manually back up running config of EU_CoreSW1 to Monitoring server | "copy running-config tftp: --> 10.3.200.18 | Writing running-config…!! OK | 2025-03-27 | OK
3.8 | Manually back up running config of EU_CoreSW2 to Monitoring server | "copy running-config tftp: --> 10.3.200.18 | Writing running-config…!! OK | 2025-03-27 | OK
3.9 | Manually back up running config of EU_AccessSW1 to Monitoring server | "copy running-config tftp: --> 10.3.200.18 | Writing running-config…!! OK | 2025-03-27 | OK
3.10 | Manually back up running config of EU_AccessSW2 to Monitoring server | "copy running-config tftp: --> 10.3.200.18 | Writing running-config…!! OK | 2025-03-27 | OK
3.11 | Check US_AccessSW_CHI config file backed up on Monitoring Server | Monitoring server --> Services --> TFTP | US_Access_CHI-confg in list | 2025-03-27 | OK
3.12 | Check US_AccessSW_NYI config file backed up on Monitoring Server | Monitoring server --> Services --> TFTP | US_Access_NY-confg in list | 2025-03-27 | OK
3.13 | Check US_Roas_CHI config file backed up on Monitoring Server | Monitoring server --> Services --> TFTP | US_Roas_CHI-confg in list | 2025-03-27 | OK
3.14 | Check US_Roas_NY config file backed up on Monitoring Server | Monitoring server --> Services --> TFTP | US_Roas_NY-confg in list | 2025-03-27 | OK
3.15 | Check US_FW_NY config file backed up on Monitoring Server | Monitoring server --> Services --> TFTP | US_FW_NY-confg in list | 2025-03-27 | OK
3.16 | Check EU_FW_BRU config file backed up on Monitoring Server | Monitoring server --> Services --> TFTP | EU_FW_BRU-confg in list | 2025-03-27 | OK
3.17 | Check EU_CoreSW1 config file backed up on Monitoring Server | Monitoring server --> Services --> TFTP | EU_CoreSW1-confg in list | 2025-03-27 | OK
3.18 | Check EU_CoreSW2 config file backed up on Monitoring Server | Monitoring server --> Services --> TFTP | EU_CoreSW2-confg in list | 2025-03-27 | OK
3.19 | Check EU_AccessSW1 config file backed up on Monitoring Server | Monitoring server --> Services --> TFTP | EU_AccessSW1-confg in list | 2025-03-27 | OK
3.20 | Check EU_AccessSW2 config file backed up on Monitoring Server | Monitoring server --> Services --> TFTP | EU_AccessSW2-confg in list | 2025-03-27 | OK
3.21 | Manually load US_AccessSW_CHI-confg file from TFTP to US_AccessSW_CHI running config | "copy tftp running-config: --> 10.3.200.18 --> US_AccessSW_CHI-confg | Accessing tftp://10.3.200.18/US_AccessSW_CHI-confg… | 2025-03-27 | OK
3.22 |  |  | Loading US_AccessSW_CHI-confg from 10.3.200.18: ! | 2025-03-27 | OK
3.23 |  |  | OK | 2025-03-27 | OK
3.24 | Manually load EU_CoreSW1-confg file from TFTP to EU_CoreSW1 running config | "copy tftp running-config: --> 10.3.200.18 --> EU_CoreSW1-confg | Accessing tftp://10.3.200.18/EU_CoreSW1-confg… | 2025-03-27 | OK
3.25 |  |  | Loading EU_CoreSW1-confg from 10.3.200.18: ! | 2025-03-27 | OK
3.26 |  |  | OK | 2025-03-27 | OK
4. CHECK CONNECTIVITY
4.1 | Test connectivity between CHI-PC01 and Monitoring Server | ping from 10.2.10.10 to 10.3.200.18 | Ping statistics: 100% reply - 0% loss | 2025-03-27 | OK
4.2 | Test connectivity between NY-PC01 and Monitoring Server | ping from 10.1.10.10 to 10.3.200.18 | Ping statistics: 100% reply - 0% loss | 2025-03-27 | OK
4.3 | Test connectivity between BRU-PC01 and Monitoring Server | ping from 10.3.10.10 to 10.3.200.18 | Ping statistics: 100% reply - 0% loss | 2025-03-27 | OK
4.4 | Test connectivity between BRU-PC02 and Monitoring Server | ping from 10.3.10.11 to 10.3.200.18 | Ping statistics: 100% reply - 0% loss | 2025-03-27 | OK
4.5

## Test Plan Fase 10 - BGPandNAT
TEST # | CATEGORY | TEST CRITERIA | RESULT | TEST DATE | OK / NOK | RE-TEST DATE | OK / NOK | NOTES
1. BGP CONFIGURATION
1.1 | Check BGP configuration on US_FW_NY | "Show running-config" | Router bgp 65100 | 2025-05-05 | OK
1.2 |  |  | neighbor 193.190.124.202 remote-as 65200 | 2025-05-05 | OK
1.5 |  | "show ip bgp summary" | BGP router identifier 193.190.124.201, local AS number 65100 | 2025-05-05 | OK
1.6 |  |  | neighbor 193.190.124.202 | 2025-05-05 | OK
1.7 |  |  | AS 65200 | 2025-05-05 | OK
1.8 | Check BGP configuration on EU_FW_BRU | "Show running-config" | Router bgp 65300 | 2025-05-05 | OK
1.9 |  |  | neighbor 193.190.124.210 remote-as 65200 | 2025-05-05 | OK
1.11 |  | "show ip bgp summary" | BGP router identifier 193.190.124.209, local AS number 65300 | 2025-05-05 | OK
1.12 |  |  | neighbor 193.190.124.210 | 2025-05-05 | OK
1.13 |  |  | AS 65200 | 2025-05-05 | OK
1.14 | Check BGP configuration on R_PROVIDER | "Show running-config" | Router bgp 65200 | 2025-05-05 | OK
1.15 |  |  | neighbor 193.190.124.201 remote-as 65100 | 2025-05-05 | OK
1.16 |  |  | neighbor 193.190.124.209 remote-as 65300 | 2025-05-05 | OK
1.19 |  | "show ip bgp summary" | BGP router identifier 193.190.124.210, local AS number 65200 | 2025-05-05 | OK
1.20 |  |  | neighbor 193.190.124.201 | 2025-05-05 | OK
1.21 |  |  | AS 65100 | 2025-05-05 | OK
1.22 |  |  | neighbor 193.190.124.209 | 2025-05-05 | OK
1.23 |  |  | AS 65300 | 2025-05-05 | OK
1.24
2. NAT CONFIGURATION
2.1 | Check NAT configuration on US_FW_NY | "Show running-config" | Interface GigabitEthernet0/0 - ip nat outside | 2025-05-05 | OK
2.2 |  |  | Interface VLAN 10 - ip nat inside | 2025-05-05 | OK
2.3 |  |  | Interface VLAN 20 - ip nat inside | 2025-05-05 | OK
2.4 |  |  | Interface VLAN 100 - ip nat inside | 2025-05-05 | OK
2.5 |  |  | Interface VLAN 200 - ip nat inside | 2025-05-05 | OK
2.6 |  |  | access-list 1 permit 10.1.10.0 0.0.0.255 | 2025-05-05 | OK |  |  | Allow New York VLAN10 to use NAT/PAT
2.7 |  |  | access-list 1 permit 10.1.20.0 0.0.0.255 | 2025-05-05 | OK |  |  | Allow New York VLAN20 to use NAT/PAT
2.8 |  |  | access-list 1 permit 10.1.100.0 0.0.0.31 | 2025-05-05 | OK |  |  | Allow New York VLAN100 to use NAT/PAT
2.9 |  |  | access-list 1 permit 10.2.10.0 0.0.0.63 | 2025-05-05 | OK |  |  | Allow Chicago VLAN10 to use NAT/PAT
2.10 |  |  | access-list 1 permit 10.2.20.0 0.0.0.63 | 2025-05-05 | OK |  |  | Allow Chicago VLAN20 to use NAT/PAT
2.11 |  |  | access-list 1 permit 10.2.100.0 0.0.0.31 | 2025-05-05 | OK |  |  | Allow Chicago VLAN100 to use NAT/PAT
2.12 |  |  | ip nat inside source list 1 interface GigabitEthernet0/0 overload | 2025-05-05 | OK |  |  | All previous defined VLANs can use Gig0/0 interface for NAT/PAT
2.13 |  |  | ip nat inside source static 10.1.200.10 193.190.124.1 | 2025-05-05 | OK |  |  | Single private IP address from VLAN200 to use dedicate public IP address
2.14 |  | "show ip nat translations" | Inside Global - 193.190.124.1 | 2025-05-05 | OK
2.15 |  |  | Inside Local - 10.1.200.10 | 2025-05-05 | OK
2.16 | Check NAT configuration on EU_FW_BRU | "Show running-config" | Interface GigabitEthernet0/0 - ip nat outside | 2025-05-05 | OK
2.17 |  |  | Interface VLAN 10 - ip nat inside | 2025-05-05 | OK
2.18 |  |  | Interface VLAN 20 - ip nat inside | 2025-05-05 | OK
2.19 |  |  | Interface VLAN 100 - ip nat inside | 2025-05-05 | OK
2.20 |  |  | Interface VLAN 200 - ip nat inside | 2025-05-05 | OK
2.21 |  |  | access-list 1 permit 10.3.10.0 0.0.0.255 | 2025-05-05 | OK |  |  | Allow Brussels VLAN10 to use NAT/PAT
2.22 |  |  | access-list 1 permit 10.3.20.0 0.0.0.255 | 2025-05-05 | OK |  |  | Allow Brussels VLAN20 to use NAT/PAT
2.23 |  |  | access-list 1 permit 10.3.100.0 0.0.0.31 | 2025-05-05 | OK |  |  | Allow Brussels VLAN100 to use NAT/PAT
2.24 |  |  | ip nat inside source list 1 interface GigabitEthernet0/0 overload | 2025-05-05 | OK |  |  | All previous defined VLANs can use Gig0/0 interface for NAT/PAT
2.25 |  |  | ip nat inside source static 10.3.200.19 193.190.124.9 | 2025-05-05 | OK |  |  | DHCP Server IP address from VLAN200 to use dedicate public IP address
2.26 |  | "show ip nat translations" | Inside Global - 193.190.124.9 | 2025-05-05 | OK
2.27 |  |  | Inside Local - 10.3.200.19 | 2025-05-05 | OK
3. IP CONFIGURATION - FWs - R_PROVIDER
3.1 | Changed IP address for US_FW_NY - R_PROVIDER connectivity | "show ip interface brief" | GigabitEthernet0/0: 193.190.124.201 | 2025-05-05 | OK |  |  | Adjusted P2P network: 193.190.124.200/30
3.2 | Changed IP address for R_PROVIDER - US_FW_NY connectivity | "show ip interface brief" | GigabitEthernet0/1: 193.190.124.202 | 2025-05-05 | OK
3.3 | Changed IP address for EU_FW_BRU - R_PROVIDER connectivity | "show ip interface brief" | GigabitEthernet0/0: 193.190.124.209 | 2025-05-05 | OK |  |  | Adjusted P2P network: 193.190.124.208/30
3.4 | Changed IP address for R_PROVIDER - EU_FW_BRU connectivity | "show ip interface brief" | GigabitEthernet0/2: 193.190.124.210 | 2025-05-05 | OK
3.5
4. CHECK CONNECTIVITY
4.1 | Test connectivity between CHI-PC01 and BRU-PC02 | ping from 10.2.10.10 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-05-05 | OK
4.2 | Test connectivity between NY-PC01 and BRU-PC02 | ping from 10.1.10.10 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-05-05 | OK
4.3 | Test connectivity between CHI-PC01 and EU_FW_BRU | ping from 10.2.10.10 to 193.190.124.209 | Ping statistics: 100% reply - 0% loss | 2025-05-05 | OK
4.4 | Test connectivity between NY-PC01 and EU_FW_BRU | ping from 10.1.10.10 to 193.190.124.209 | Ping statistics: 100% reply - 0% loss | 2025-05-05 | OK
4.5 | Test connectivity between BRU-PC01 and US_FW_NY | ping from 10.3.10.10 to 193.190.124.201 | Ping statistics: 100% reply - 0% loss | 2025-05-05 | OK
4.6 | Test connectivity between BRU-PC01 and US_FW_NY | ping from 10.3.10.11 to 193.190.124.201 | Ping statistics: 100% reply - 0% loss | 2025-05-05 | OK
4.7 | Test connectivity between BRU-PC01 and R_PROVIDER | ping from 10.3.10.11 to 193.190.124.210 | Ping statistics: 100% reply - 0% loss | 2025-05-05 | OK
4.8 | Test connectivity between NY-PC01 and R_PROVIDER | ping from 10.1.10.10 to 193.190.124.202 | Ping statistics: 100% reply - 0% loss | 2025-05-05 | OK
4.9 | Test connectivity between NY-PC01 and DHCP Server | ping from 10.1.10.10 to 10.3.200.19 | Ping statistics: 100% reply - 0% loss | 2025-05-05 | OK

## Test Plan Fase 11 - ACL
TEST # | CATEGORY | TEST CRITERIA | RESULT | TEST DATE | OK / NOK | RE-TEST DATE | OK / NOK | NOTES
1. PORT SECURITY CONFIGURATION ON ACCESS SWITCHES
1.1 | Check port security configuration on EU_AccessSW1 | "show port-security" | Interfaces Fa0/3-22 have port-security enabled, with Max MAC address count 2 | 2025-05-15 | OK
1.2 | Check port security configuration on EU_AccessSW2 | "show port-security" | Interfaces Fa0/3-22 have port-security enabled, with Max MAC address count 2 | 2025-05-15 | OK
1.3 | Check port security configuration on US_AccessSW_NY | "show port-security" | Interfaces Fa0/2-21 have port-security enabled, with Max MAC address count 2 | 2025-05-15 | OK
1.4 | Check port security configuration on US_AccessSW_CHI | "show port-security" | Interfaces Fa0/2-21 have port-security enabled, with Max MAC address count 2 | 2025-05-15 | OK
1.5 | Check Security Action is taken after count violation | Add 2 other devices to interface - should go "down" | Interface Fa0/13 went down | 2025-05-15 | OK
1.6 |  | "show port-security interface Fa0/13" | Port Status: Secure-shutdown | 2025-05-15 | OK
1.7
2. DHCP SNOOPING CONFIGURATION
2.1 | Check dhcp snooping configuration on EU_AccessSW1 | "show running-config" | ip dhcp snooping vlan 10 | 2025-05-15 | OK
2.2 | Check dhcp snooping configuration on EU_AccessSW2 | "show running-config" | ip dhcp snooping vlan 10 | 2025-05-15 | OK
2.3 | Check dhcp snooping configuration on EU_CoreSW1 | "show running-config" | ip dhcp snooping vlan 10 | 2025-05-15 | OK
2.4 | Check dhcp snooping configuration on EU_CoreSW2 | "show running-config" | ip dhcp snooping vlan 10 | 2025-05-15 | OK
2.5 | Check trusted interfaces on EU_AccessSW1 | "show ip dhcp snooping" | Switch DHCP snooping is enabled | 2025-05-15 | OK
2.6 |  |  | Interface Fa0/1: Trusted - YES | 2025-05-15 | OK |  |  | Fa0/1 is the interface linked to EU_CoreSW1
2.7 |  |  | Interface Fa0/2: Trusted - YES | 2025-05-15 | OK |  |  | Fa0/2 is the interface linked to EU_CoreSW2
2.8 |  |  | Interface Fa0/18: Trusted - YES | 2025-05-15 | OK |  |  | Fa0/18 is the interface connected to the DHCP server
2.9 |  |  | Interface Fa0/7: Trusted - NO | 2025-05-15 | OK |  |  | Fa0/7 is the interface linked to BRU-DhcpTest2 device
2.10 | Check binded dhcp IP addresses on EU_AccessSW1 | "show ip dhcp snooping binding" | IpAddress within VLAN10 | 2025-05-15 | OK
2.11 |  |  | Interface Fa0/7 - BRU-DhcpTest2 device | 2025-05-15 | OK
2.12 | Check trusted interfaces on EU_AccessSW2 | "show ip dhcp snooping" | Switch DHCP snooping is enabled | 2025-05-15 | OK
2.13 |  |  | Interface Fa0/1: Trusted - YES | 2025-05-15 | OK |  |  | Fa0/1 is the interface linked to EU_CoreSW1
2.14 |  |  | Interface Fa0/2: Trusted - YES | 2025-05-15 | OK |  |  | Fa0/2 is the interface linked to EU_CoreSW2
2.15 |  |  | Interface Fa0/7: Trusted - NO | 2025-05-15 | OK |  |  | Fa0/7 is the interface linked to BRU-DhcpTest1 device
2.16 | Check binded dhcp IP addresses on EU_AccessSW2 | "show ip dhcp snooping binding" | IpAddress within VLAN10 | 2025-05-15 | OK |  |  | IP address distributed to BRU-DhcpTest1 device
2.17 |  |  | Interface Fa0/7 - BRU-DhcpTest1 device | 2025-05-15 | OK
2.18 | Check trusted interfaces on EU_CoreSW1 | "show ip dhcp snooping" | Switch DHCP snooping is enabled | 2025-05-15 | OK
2.19 |  |  | Interface Fa0/2: Trusted - YES | 2025-05-15 | OK |  |  | Fa0/2 is the interface (port-channel1) linked to EU_CoreSW2
2.20 |  |  | Interface Fa0/3: Trusted - YES | 2025-05-15 | OK |  |  | Fa0/3 is the interface (port-channel1) linked to EU_CoreSW2
2.21 |  |  | Interface Fa0/4: Trusted - YES | 2025-05-15 | OK |  |  | Fa0/4 is the interface linked to EU_CoreSW2
2.22 |  |  | Interface Fa0/5: Trusted - YES | 2025-05-15 | OK |  |  | Fa0/5 is the interface linked to EU_CoreSW1
2.23 | Check trusted interfaces on EU_CoreSW2 | "show ip dhcp snooping" | Switch DHCP snooping is enabled | 2025-05-15 | OK
2.24 |  |  | Interface Fa0/2: Trusted - YES | 2025-05-15 | OK |  |  | Fa0/2 is the interface (port-channel1) linked to EU_CoreSW1
2.25 |  |  | Interface Fa0/3: Trusted - YES | 2025-05-15 | OK |  |  | Fa0/3 is the interface (port-channel1) linked to EU_CoreSW1
2.26 |  |  | Interface Fa0/4: Trusted - YES | 2025-05-15 | OK |  |  | Fa0/4 is the interface linked to EU_CoreSW1
2.27 |  |  | Interface Fa0/5: Trusted - YES | 2025-05-15 | OK |  |  | Fa0/5 is the interface linked to EU_CoreSW2
2.28
3. ACCESS CONTROL LIST (ACL) CONFIGURATION
3.1 | No data allowed to pass between data VLAN's (VLAN 10) | Ping from 10.1.10.10 to 10.2.10.10 - should fail | Reply from 10.1.10.1: Destination host unreachable. | 2025-05-15 | OK
3.2 |  | Ping from 10.1.10.10 to 10.3.10.10 - should fail | Reply from 10.1.10.1: Destination host unreachable. | 2025-05-15 | OK
3.3 |  | Ping from 10.2.10.10 to 10.1.10.10 - should fail | Reply from 10.2.10.1: Destination host unreachable. | 2025-05-15 | OK
3.4 |  | Ping from 10.2.10.10 to 10.3.10.10 - should fail | Reply from 10.2.10.1: Destination host unreachable. | 2025-05-15 | OK
3.5 |  | Ping from 10.3.10.10 to 10.1.10.10 - should fail | Reply from 10.3.10.3: Destination host unreachable | 2025-05-15 | OK
3.6 |  | Ping from 10.3.10.10 to 10.2.10.10 - should fail | Reply from 10.3.10.3: Destination host unreachable | 2025-05-15 | OK
3.7 | Data allowed to pass between VLAN's | Ping from 10.1.10.10 to 10.3.200.18 (Monitoring server, VLAN 200) | Reply from 10.3.200.18: 0% loss | 2025-05-15 | OK
3.8 |  | Ping from 10.2.10.10 to 10.3.200.18 (Monitoring server, VLAN 200) | Reply from 10.3.200.18: 0% loss | 2025-05-15 | OK
3.9 |  | Ping from 10.3.10.10 to 10.3.200.18 (Monitoring server, VLAN 200) | Reply from 10.3.200.18: 0% loss | 2025-05-15 | OK
3.10 | DHCP traffic is allowed for DHCP server - EU_CoreSW1 | "show ip access-list 101" | Permit DHCP-traffic from any device to the DHCP server | 2025-05-15 | OK
3.11 |  |  | Permits DHCP-response from DHCP server to device | 2025-05-15 | OK
3.12 |  |  | Denies any other DHCP-traffic to and from any other server than the legit (10.3.200.19) | 2025-05-15 | OK
3.13 | DHCP traffic is allowed for DHCP server - EU_CoreSW2 | "show ip access-list 101" | Permit DHCP-traffic from any device to the DHCP server | 2025-05-15 | OK
3.14 |  |  | Permits DHCP-response from DHCP server to device | 2025-05-15 | OK
3.15 |  |  | Denies any other DHCP-traffic to and from any other server than the legit (10.3.200.19) | 2025-05-15 | OK
3.16 | Check if any other "rogue" DHCP server is able to respond | Change IP address of DHCP server to 10.3.200.20. Reconnect BRU-DhcpTest2 and this should not get an IP address assigned | BRU-DhcpTest2 device gets local IP address of 169.254.208.26 and doesn't get an IP address from the VLAN10 range | 2025-05-15 | OK
3.17
3.18 | Secure remote access to NEW YORK network devices from Mgmt PC | SSH from 10.1.100.30 to 10.1.100.10 (US_AccessSW_NY) - should work | SSH connection successful | 2025-05-15 | OK
3.19 |  | SSH from 10.1.100.30 to 10.1.100.1 (US_Roas_NY) - should work | SSH connection successful | 2025-05-15 | OK
3.20 |  | SSH from 10.1.100.30 to 172.16.1.1 (US_FW_NY) - should work | SSH connection successful | 2025-05-15 | OK
3.21 |  | SSH from 10.1.10.10 to 10.1.100.10 (US_AccessSW_NY) - should NOT work | Unable to establish SSH connection | 2025-05-15 | OK
3.22 |  | SSH from 10.1.10.10 to 10.1.100.1 (US_Roas_NY) - should NOT work | Unable to establish SSH connection | 2025-05-15 | OK
3.23 |  | SSH from 10.1.10.10 to 172.16.1.1 (US_FW_NY) - should NOT work | Unable to establish SSH connection | 2025-05-15 | OK
3.24 | Secure remote access to CHICAGO network devices from Mgmt PC | SSH from 10.2.100.30 to 10.2.100.10 (US_AccessSW_CHI) - should work | SSH connection successful | 2025-05-15 | OK
3.25 |  | SSH from 10.2.100.30 to 10.2.100.1 (US_Roas_CHI) - should work | SSH connection successful | 2025-05-15 | OK
3.26 |  | SSH from 10.2.10.10 to 10.2.100.10 (US_AccessSW_CHI) - should NOT work | Unable to establish SSH connection | 2025-05-15 | OK
3.27 |  | SSH from 10.2.10.10 to 10.2.100.1 (US_Roas_CHI) - should NOT work | Unable to establish SSH connection | 2025-05-15 | OK
3.28 | Secure remote access to BRUSSELS network devices from Mgmt PC | SSH from 10.3.100.30 to 10.3.100.12 (EU_AccessSW1) - should work | SSH connection successful | 2025-05-15 | OK
3.29 |  | SSH from 10.3.100.30 to 10.3.100.13 (EU_AccessSW2) - should work | SSH connection successful | 2025-05-15 | OK
3.30 |  | SSH from 10.3.100.30 to 10.3.100.3 (EU_CoreSW1) - should work | SSH connection successful | 2025-05-15 | OK
3.31 |  | SSH from 10.3.100.30 to 10.3.100.4 (EU_CoreSW1) - should work | SSH connection successful | 2025-05-15 | OK
3.32 |  | SSH from 10.3.100.30 to 172.16.1.13 (EU_FW_BRU) - should work | SSH connection successful | 2025-05-15 | OK
3.33 |  | SSH from 10.3.10.10 to 10.3.100.12 (EU_AccessSW1) - should NOT work | Unable to establish SSH connection | 2025-05-15 | OK
3.34 |  | SSH from 10.3.10.10 to 10.3.100.13 (EU_AccessSW2) - should NOT work | Unable to establish SSH connection | 2025-05-15 | OK
3.35 |  | SSH from 10.3.10.10 to 10.3.100.3 (EU_CoreSW1) - should NOT work | Unable to establish SSH connection | 2025-05-15 | OK
3.36 |  | SSH from 10.3.10.10 to 10.3.100.4 (EU_CoreSW1) - should NOT work | Unable to establish SSH connection | 2025-05-15 | OK
3.37 |  | SSH from 10.3.10.10 to 172.16.1.13 (EU_FW_BRU) - should NOT work | Unable to establish SSH connection | 2025-05-15 | OK
3.38
4. FIREWALL POLICIES
4.1 | Policy on EU_FW_BRU | Policy that denies all data traffic between DATA VLANs (VLAN10) |  | 2025-05-15 | OK
4.2
4.3
4.4
4.5
4.6 |  | Policy that limits remote access from the 10.3.100.30 address (mgmt pc) |  | 2025-05-15 | OK
4.7
4.8
4.9
4.10
4.11
4.12
4.13
4.14 | Policy on EU_FW_BRU | Policy that denies all data traffic between DATA VLANs (VLAN10) |  | 2025-05-15 | OK
4.15
4.16
4.17
4.18
4.19 |  | Policy that limits remote access from the 10.1.100.30 address (mgmt pc) |  | 2025-05-15 | OK
4.20
4.21
4.22
4.23
4.24
4.25
4.26