## Test Plan Fase 2 - Roas
TEST # | CATEGORY | TEST CRITERIA | RESULT | TEST DATE | OK / NOK | RE-TEST DATE | OK / NOK | NOTES
1. Local Connectivity
1.1 | Check US_Roas_CHI link health | Gi0/0.10: ping 10.2.10.1 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.2 |  | Gi0/0.20: ping 10.2.20.1 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.3 |  | Gi0/0.100: ping 10.2.100.1 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.4 |  | Gi0/0.200: ping 10.2.200.1 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.5 | Check US_Roas_NY link health | Gi0/0.10: ping 10.1.10.1 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.6 |  | Gi0/0.20: ping 10.1.20.1 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.7 |  | Gi0/0.100: ping 10.1.100.1 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.8 |  | Gi0/0.200: ping 10.1.200.1 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.9 | Test connectivity between CHI and NY PCs | ping from 10.2.10.10 to 10.1.10.10 | Ping statistics: 100% reply - 0% loss | 2025-02-20 | OK
1.10
2. Routing Tables
2.1 | Check static routes for US_Roas_CHI | "show ip route" | Static route for 10.1.0.0/16 via 172.16.1.10 | 2025-02-20 | OK
2.2 | Check static routes for US_Roas_NY | "show ip route" | Static route for 10.2.0.0/16 via 172.16.1.9 | 2025-02-20 | OK
2.3
3. Local Connectivity
3.1 | Locally connect to US_Roas_CHI | Connect laptop to device with console cable | able to connect via Putty | 2025-02-20 | OK
3.2 | Locally connect to US_Roas_NY | Connect laptop to device with console cable | able to connect via Putty | 2025-02-20 | OK
3.3 | Locally connect to US_AccessSW_CHI | Connect laptop to device with console cable | able to connect via Putty | 2025-02-20 | OK
3.4 | Locally connect to US_AccessSW_NY | Connect laptop to device with console cable | able to connect via Putty | 2025-02-20 | OK
3.5
4. VLAN Configuation
4.1 | Check VLAN config on US_AccessSW_CHI | "show vlan brief" | VLANs 10,20,100 and 200 in overview | 2025-02-20 | OK
4.2 | Check VLAN config on US_AccessSW_NY | "show vlan brief" | VLANs 10,20,100 and 200 in overview | 2025-02-20 | OK
4.3 | Check trunking on US_AccessSW_CHI | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed | 2025-02-20 | OK
4.4 | Check trunking on US_AccessSW_NY | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed | 2025-02-20 | OK
4.5 | Check subinterfaces on US_Roas_CHI | "show ip interface brief" | Subinterfaces for VLANs 10,20,100,200 are configures | 2025-02-20 | OK
4.6 | Check subinterfaces on US_Roas_NY | "show ip interface brief" | Subinterfaces for VLANs 10,20,100,200 are configures | 2025-02-20 | OK
4.7
5. Device and connection security
5.1 | VTY lines secured | "show running config" | password set and login required | 2025-02-20 | OK
5.2 | Unused ports disabled | "show interface status" | unused ports "disabled" | 2025-02-20 | OK
5.3 | Username and password set | Connect laptop to device with console cable | Prompt for username and password | 2025-02-20 | OK
5.4
6. SSH Testing between devices
6.1 | US_Access_SW_CHI → US_Roas_CHI | ssh -l admin 10.2.100.1 | able to connect via SSH after providing credentials | 2025-02-25 | OK
6.2 | US_Roas_CHI → US_Roas_NY | ssh -l admin 10.1.100.1 | able to connect via SSH after providing credentials | 2025-02-25 | OK
6.3 | US_Roas_NY → US_AccessSW_NY | ssh -l admin 10.1.100.10 | able to connect via SSH after providing credentials | 2025-02-25 | OK
6.4
7.
7.1
7.2
7.3

## Test Plan Fase 3 - Collaps_Core
TEST # | CATEGORY | TEST CRITERIA | RESULT | TEST DATE | OK / NOK | RE-TEST DATE | OK / NOK | NOTES
1. Local Connectivity
1.1 | Check EU_CoreSW1 link health | VLAN10_SVI: ping 10.3.10.3 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.2 |  | VLAN20_SVI: ping 10.3.20.3 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.3 |  | VLAN100_SVI: ping 10.3.100.3 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.4 |  | VLAN200_SVI: ping 10.3.200.3 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.5 | Check EU_CoreSW2 link health | VLAN10_SVI: ping 10.3.10.4 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.6 |  | VLAN20_SVI: ping 10.3.20.4 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.7 |  | VLAN100_SVI: ping 10.3.100.4 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.8 |  | VLAN200_SVI: ping 10.3.200.4 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.9 | Check EU_CoreSW - HSRP link healt | VLAN10: ping 10.3.10.5 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.10 |  | VLAN20: ping 10.3.20.5 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.11 |  | VLAN100: ping 10.3.100.5 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.12 |  | VLAN200: ping 10.3.200.5 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.13 | Check EU_AccessSW1 link health | ping 10.3.100.12 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.14 | Check EU_AccessSW2 link health | ping 10.3.100.13 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.15 | Test connectivity between BRU-PC01 and BRU-PC02 | ping from 10.3.10.10 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.16
2. Routing Tables
2.1 | Check static routes for EU_CoreSW1 | "show ip route" | All VLAN networks + subnet "connected" | 2025-03-05 | OK |  |  | All VLAN subnets are "connected" (C)
2.2 | Check static routes for EU_CoreSW2 | "show ip route" | All VLAN networks + subnet "connected" | 2025-03-05 | OK |  |  | All VLAN subnets are "connected" (C)
2.3
3. Local Connectivity
3.1 | Locally connect to EU_CoreSW1 | Connect laptop to device with console cable | able to connect via Putty | 2025-03-05 | OK
3.2 | Locally connect to EU_CoreSW2 | Connect laptop to device with console cable | able to connect via Putty | 2025-03-05 | OK
3.3 | Locally connect to EU_AccessSW1 | Connect laptop to device with console cable | able to connect via Putty | 2025-03-05 | OK
3.4 | Locally connect to EU_AccessSW2 | Connect laptop to device with console cable | able to connect via Putty | 2025-03-05 | OK
3.5
4. VLAN Configuation
4.1 | Check VLAN config on EU_AccessSW1 | "show vlan brief" | VLANs 10,20,100 and 200 + names in overview | 2025-03-05 | OK |  |  | VLANs defined
4.2 | Check VLAN config on EU_AccessSW2 | "show vlan brief" | VLANs 10,20,100 and 200 + names in overview | 2025-03-05 | OK |  |  | VLANs defined
4.3 | Check VLAN config on EU_CoreSW1 | "show vlan brief" | VLANs 10,20,100 and 200 + names in overview | 2025-03-05 | OK |  |  | VLANs defined
4.4 | Check VLAN config on EU_CoreSW2 | "show vlan brief" | VLANs 10,20,100 and 200 + names in overview | 2025-03-05 | OK |  |  | VLANs defined
4.5 | Check trunking on EU_AccessSW1 | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed on trunk interfaces | 2025-03-05 | OK |  |  | Allowed on Fa0/1, Fa0/2
4.6 | Check trunking on EU_AccessSW2 | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed on trunk interfaces | 2025-03-05 | OK |  |  | Allowed on Fa0/1, Fa0/2
4.7 | Check trunking on EU_CoreSW1 | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed on trunk interfaces | 2025-03-05 | OK |  |  | Allowed on Po1, Fa0/4, Fa0/5
4.8 | Check trunking on EU_CoreSW2 | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed on trunk interfaces | 2025-03-05 | OK |  |  | Allowed on Po1, Fa0/4, Fa0/5
4.9 | Check subinterfaces on EU_CoreSW1 | "show ip interface brief" | Subinterfaces for VLANs 10,20,100,200 are configures | 2025-03-05 | OK |  |  | SVIs defined
4.10 | Check subinterfaces on EU_CoreSW2 | "show ip interface brief" | Subinterfaces for VLANs 10,20,100,200 are configures | 2025-03-05 | OK |  |  | SVIs defined
4.11
5. Device and connection security
5.1 | VTY lines secured on EU_CoreSW1 | "show running-config" | password set and login required | 2025-03-05 | OK |  |  | CLI prompts credentials
5.2 | VTY lines secured on EU_CoreSW2 | "show running-config" | password set and login required | 2025-03-05 | OK |  |  | CLI prompts credentials
5.3 | VTY lines secured on EU_AccessSW1 | "show running-config" | password set and login required | 2025-03-05 | OK |  |  | CLI prompts credentials
5.4 | VTY lines secured on EU_AccessSW2 | "show running-config" | password set and login required | 2025-03-05 | OK |  |  | CLI prompts credentials
5.5 | Unused ports disabled on EU_CoreSW1 | "show interface status" | unused ports "disabled" | 2025-03-05 | OK
5.6 | Unused ports disabled on EU_CoreSW2 | "show interface status" | unused ports "disabled" | 2025-03-05 | OK
5.7 | Unused ports disabled on EU_AccessSW1 | "show interface status" | unused ports "disabled" | 2025-03-05 | OK
5.8 | Unused ports disabled on EU_AccessSW2 | "show interface status" | unused ports "disabled" | 2025-03-05 | OK
5.9 | Username and password set on EU_CoreSW1 | Connect to CLI (or via SSH) | Prompt for username and password | 2025-03-05 | OK
5.10 | Username and password set on EU_CoreSW2 | Connect to CLI (or via SSH) | Prompt for username and password | 2025-03-05 | OK
5.11 | Username and password set on EU_AccessSW1 | Connect to CLI (or via SSH) | Prompt for username and password | 2025-03-05 | OK
5.12 | Username and password set on EU_AccessSW2 | Connect to CLI (or via SSH) | Prompt for username and password | 2025-03-05 | OK
5.13 | Passwords encrypted in config files for EU_CoreSW1 | "show running-config" | Passwords encrypted + "service password encryption" | 2025-03-05 | OK
5.14 | Passwords encrypted in config files for EU_CoreSW2 | "show running-config" | Passwords encrypted + "service password encryption" | 2025-03-05 | OK
5.15 | Passwords encrypted in config files for EU_AccessSw1 | "show running-config" | Passwords encrypted + "service password encryption" | 2025-03-05 | OK
5.16 | Passwords encrypted in config files for EU_AccessSw2 | "show running-config" | Passwords encrypted + "service password encryption" | 2025-03-05 | OK
5.17
6. SSH Configuration
6.1 | EU_AccessSW1 → EU_AccessSW2 | ssh -l admin 10.3.100.13 | able to connect via via SSH, password prompted and access granted | 2025-03-05 | OK
6.2 | EU_CoreSW1 → EU_CoreSW2.vlan10 | ssh -l admin 10.3.10.4 | able to connect via via SSH, password prompted and access granted | 2025-03-05 | OK
6.3 | EU_AccessSW2 → EU_CoreSW1.vlan20 | ssh -l admin 10.3.20.3 | able to connect via via SSH, password prompted and access granted | 2025-03-05 | OK
6.4 | EU_CoreSW2 → EU_AccessSW1 | ssh -l admin 10.3.100.12 | able to connect via via SSH, password prompted and access granted | 2025-03-05 | OK
6.5
7. Spanning Tree Protocol
7.1 | Rapid-PVST enabled on EU_CoreSW1 | "show running-config" | "spanning-tree mode rapid-pvst" | 2025-03-05 | OK |  |  | Priority 0 - root bridge
7.2 | Rapid-PVST enabled on EU_CoreSW2 | "show running-config" | "spanning-tree mode rapid-pvst" | 2025-03-05 | OK |  |  | Priority 4096 - secondary root bridge
7.3 | Rapid-PVST enabled on EU_AccessSW1 | "show running-config" | "spanning-tree mode rapid-pvst" | 2025-03-05 | OK
7.4 | Rapid-PVST enabled on EU_AccessSW2 | "show running-config" | "spanning-tree mode rapid-pvst" | 2025-03-05 | OK
7.5 | Ensure path changes when link is broken | Disable link between EU_CoreSW1 and EU_AccessSW2 | Packet from BRU-PC01 to BRU-PC02 takes different route | 2025-03-05 | OK |  |  | Normal route: BRU-PC01 - EU_AccessSW1 - EU_CoreSW1 - EU_AccessSW2 - BRU-PC02 New route: BRU-PC01 - EU_AccessSW1 - EU_CoreSW1 - EU_CoreSW2 - EU_AccessSW2 - BRU-PC02
7.6 | BPDU Guard enabled on EU_CoreSW1 | "show running-config" | "spanning-tree portfast bpduguard default" | 2025-03-05 | OK
7.7 | BPDU Guard enabled on EU_CoreSW2 | "show running-config" | "spanning-tree portfast bpduguard default" | 2025-03-05 | OK
7.8 | BPDU Guard enabled on EU_AccessSW1 | "show running-config" | "spanning-tree portfast bpduguard default" | 2025-03-05 | OK
7.9 | BPDU Guard enabled on EU_AccessSW2 | "show running-config" | "spanning-tree portfast bpduguard default" | 2025-03-05 | OK
7.10
8. Etherchannel
8.1 | Etherchannel enabled on EU_CoreSW1 | "show running-config" | Interface Portchannel1 defined + interfaces Fa0/2 + Fa0/3 part of Po1 | 2025-03-05 | OK
8.2 | Etherchannel enabled on EU_CoreSW1 | "show running-config" | Interface Portchannel1 defined + interfaces Fa0/2 + Fa0/3 part of Po1 | 2025-03-05 | OK
8.3 | Etherchannel enabled on EU_CoreSW2 | "show etherchannel summary" | Po1 details + interfaces Fa0/2 + Fa0/3 in port-channel | 2025-03-05 | OK
8.4 | Etherchannel enabled on EU_CoreSW2 | "show etherchannel summary" | Po1 details + interfaces Fa0/2 + Fa0/3 in port-channel | 2025-03-05 | OK
8.5
9. Hot Standby Routing Protocol (HSRP)
9.1 | HSRP enabled on EU_CoreSW1 | "show standby" | "state is active" for all VLANs | 2025-03-05 | OK
9.2 | HSRP enabled on EU_CoreSW2 | "show standby" | "state is standby" for all VLANs | 2025-03-05 | OK
9.3

## Test Plan Fase 4 - Static_R (2)
TEST # | CATEGORY | TEST CRITERIA | RESULT | TEST DATE | OK / NOK | RE-TEST DATE | OK / NOK | NOTES
1. Local Connectivity
1.1 | Check US_FW_NY link health | ping 172.16.1.1 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.2 |  | ping 172.16.1.5 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.3 |  | ping 172.16.1.22 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.4 | Check EU_FW_BRU link health | ping 172.16.1.13 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.5 |  | ping 172.16.1.17 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.6 |  | ping 172.16.1.21 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.7 | Test connectivity between CHI-PC01 and BRU-PC02 | ping from 10.2.10.10 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.8 | Test connectivity between NY-PC01 and BRU-PC02 | ping from 10.1.10.10 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.9 | Test connectivity between CHI-PC01 and EU_FW_BRU | ping from 10.2.10.10 to 172.16.1.21 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.10 | Test connectivity between NY-PC01 and EU_FW_BRU | ping from 10.1.10.10 to 172.16.1.21 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.11 | Test connectivity between BRU-PC01 and US_FW_NY | ping from 10.3.10.10 to 172.16.1.22 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.12 | Test connectivity between BRU-PC02 and US_FW_NY | ping from 10.3.10.11 to 172.16.1.22 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
1.13
2. Routing Tables
2.1 | Check static routes for US_FW_NY | "show ip route" | All Point-to-Point networks and Last Resort "connected" | 2025-03-13 | OK |  |  | All Point-to-Point networks "connected" (C) and all static routes to the subnets "static" (S)
2.2 | Check static routes for EU_FW_BRU | "show ip route" | All Point-to-Point networks and Last Resort "connected" | 2025-03-13 | OK |  |  | All Point-to-Point networks "connected" (C) and all static routes to the subnets "static" (S)
2.3
3. Local Connectivity
3.1 | Locally connect to US_FW_NY | Connect laptop to device with console cable | able to connect via Putty | 2025-03-13 | OK
3.2 | Locally connect to EU_FW_BRU | Connect laptop to device with console cable | able to connect via Putty | 2025-03-13 | OK
3.3
4. Device and connection security
4.1 | VTY lines secured on US_FW_NY | "show running-config" | password set and login required | 2025-03-13 | OK
4.2 | VTY lines secured on EU_FW_BRU | "show running-config" | password set and login required | 2025-03-13 | OK
4.3 | Unused ports disabled on US_FW_NY | "show interface status" | unused ports "shutdown" | 2025-03-13 | OK
4.4 | Unused ports disabled on EU_FW_BRU | "show interface status" | unused ports "shutdown" | 2025-03-13 | OK
4.5 | Username and password set on US_FW_NY | Connect to CLI (or via SSH) | Prompt for username and password | 2025-03-13 | OK
4.6 | Username and password set on EU_FW_BRU | Connect to CLI (or via SSH) | Prompt for username and password | 2025-03-13 | OK
4.7 | Passwords encrypted in config files for US_FW_NY | "show running-config" | Passwords encrypted + "service password encryption" | 2025-03-13 | OK
4.8 | Passwords encrypted in config files for EU_FW_BRU | "show running-config" | Passwords encrypted + "service password encryption" | 2025-03-13 | OK
4.9
5. SSH Configuration
5.1 | EU_AccessSW1 → EU_FW_BRU | ssh -l admin 172.16.1.13 | able to connect via via SSH, password prompted and access granted | 2025-03-13 | OK
5.2 | EU_AccessSW2 → EU_FW_BRU | ssh -l admin 172.16.1.17 | able to connect via via SSH, password prompted and access granted | 2025-03-13 | OK
5.3 | US_AccessSW_CHI → US_FW_NY | ssh -l admin 172.16.1.5 | able to connect via via SSH, password prompted and access granted | 2025-03-13 | OK
5.4 | US_AccessSW_NY → US_FW_NY | ssh -l admin 172.16.1.1 | able to connect via via SSH, password prompted and access granted | 2025-03-13 | OK
5.5
6. US DHCP
7.1 | Connect device to Fa0/4 on US_AccessSW_CHI | ip address in range 10.2.10.0/26 | IP address 10.2.10.3, Gateway 10.2.10.1 | 2025-03-13 | OK
7.2 | Connect device to Fa0/5 on US_AccessSW_CHI | ip address in range 10.2.10.0/26 | IP address 10.2.10.2, Gateway 10.2.10.1 | 2025-03-13 | OK
7.3 | Connect device to Fa0/4 on US_AccessSW_NY | ip address in range 10.1.10.0/24 | IP address 10.1.10.3, Gateway 10.1.10.1 | 2025-03-13 | OK
7.4 | Connect device to Fa0/5 on US_AccessSW_NY | ip address in range 10.1.10.0/24 | IP address 10.1.10.2, Gateway 10.1.10.1 | 2025-03-13 | OK
7.5
7.6 | Ping from CHI-DHCP_1 to BRU-PC01 | ping from 10.2.10.2 to 10.3.10.10 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
7.7 | Ping from CHI-DHCP_2 to BRU-PC01 | ping from 10.2.10.3 to 10.3.10.10 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
7.8 | Ping from NY-DHCP_1 to BRU-PC02 | ping from 10.1.10.3 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
7.9 | Ping from NY-DHCP_2 to BRU-PC02 | ping from 10.1.10.2 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-13 | OK
7.10

## Test Plan Fase 5 - CentralDHCP
TEST # | CATEGORY | TEST CRITERIA | RESULT | TEST DATE | OK / NOK | RE-TEST DATE | OK / NOK | NOTES
1. EU CENTRAL DHCP
1.1 | Connect device to Fa0/7 on EU_AccessSW1 - DhcpTest2 | ip address in range 10.3.10.0/23 | IP address 10.3.10.7, Gateway 10.3.10.5 | 2025-03-14 | OK
1.2 | Connect device to Fa0/7 on EU_AccessSW2 - DhcpTest1 | ip address in range 10.3.10.0/23 | IP address 10.3.10.6, Gateway 10.3.10.5 | 2025-03-14 | OK
1.3
1.4 | Ping from DhcpTest1 to BRU-PC01 | ping from 10.2.10.6 to 10.3.10.10 | Ping statistics: 100% reply - 0% loss | 2025-03-14 | OK
1.5 | Ping from DhcpTest1 to CHI-PC01 | ping from 10.2.10.6 to 10.2.10.10 | Ping statistics: 100% reply - 0% loss | 2025-03-14 | OK
1.6 | Ping from DhcpTest1 to NY-PC01 | ping from 10.2.10.6 to 10.1.10.10 | Ping statistics: 100% reply - 0% loss | 2025-03-14 | OK
1.7 | Ping from DhcpTest2 to BRU-PC02 | ping from 10.2.10.7 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-14 | OK
1.8 | Ping from DhcpTest2 to CHI-PC01 | ping from 10.2.10.7 to 10.2.10.10 | Ping statistics: 100% reply - 0% loss | 2025-03-14 | OK
1.9 | Ping from DhcpTest2 to NY-PC01 | ping from 10.2.10.7 to 10.1.10.10 | Ping statistics: 100% reply - 0% loss | 2025-03-14 | OK
1.10

## Test Plan Fase 6 - OSPF LAN WAN
TEST # | CATEGORY | TEST CRITERIA | RESULT | TEST DATE | OK / NOK | RE-TEST DATE | OK / NOK | NOTES
1. OSPF CONFIGURATION
1.1 | Check OSPF configuration on US_FW_NY | "Show running-config" | Interface Gig0/0 - ip ospf network point-to-point | 2025-03-20 | OK
1.2 |  |  | Interface Gig0/1 - ip ospf network point-to-point | 2025-03-20 | OK
1.3 |  |  | Interface Gig0/2 - ip ospf network point-to-point | 2025-03-20 | OK
1.4 |  |  | Router ospf 10 - network 172.16.1.1 0.0.0.0 araea 0 | 2025-03-20 | OK
1.5 |  |  | Router ospf 10 - network 172.16.1.5 0.0.0.0 araea 0 | 2025-03-20 | OK
1.6 |  |  | Router ospf 10 - network 172.16.1.22 0.0.0.0 araea 0 | 2025-03-20 | OK
1.7 | Check OSPF configuration on US_Roas_CHI | "Show running-config" | Interface Gig0/1 - ip ospf network point-to-point | 2025-03-20 | OK
1.8 |  |  | Interface Gig0/2 - ip ospf network point-to-point | 2025-03-20 | OK
1.9 |  |  | Router ospf 10 - network 172.16.1.6 0.0.0.0 area 0 | 2025-03-20 | OK
1.10 |  |  | Router ospf 10 - network 172.16.1.9 0.0.0.0 area 0 | 2025-03-20 | OK
1.11 |  |  | Router ospf 10 - network 10.2.10.1 0.0.0.0 area 0 | 2025-03-20 | OK
1.12 |  |  | Router ospf 10 - network 10.2.20.1 0.0.0.0 area 0 | 2025-03-20 | OK
1.13 |  |  | Router ospf 10 - network 10.2.100.1 0.0.0.0 area 0 | 2025-03-20 | OK
1.14 |  |  | Router ospf 10 - network 10.2.200.1 0.0.0.0 area 0 | 2025-03-20 | OK
1.15 | Check OSPF configuration on US_Roas_CHI | "Show running-config" | Interface Gig0/1 - ip ospf network point-to-point | 2025-03-20 | OK
1.16 |  |  | Interface Gig0/2 - ip ospf network point-to-point | 2025-03-20 | OK
1.17 |  |  | Router ospf 10 - network 172.16.1.2 0.0.0.0 area 0 | 2025-03-20 | OK
1.18 |  |  | Router ospf 10 - network 172.16.1.10 0.0.0.0 area 0 | 2025-03-20 | OK
1.19 |  |  | Router ospf 10 - network 10.1.10.1 0.0.0.0 area 0 | 2025-03-20 | OK
1.20 |  |  | Router ospf 10 - network 10.1.20.1 0.0.0.0 area 0 | 2025-03-20 | OK
1.21 |  |  | Router ospf 10 - network 10.1.100.1 0.0.0.0 area 0 | 2025-03-20 | OK
1.22 |  |  | Router ospf 10 - network 10.1.200.1 0.0.0.0 area 0 | 2025-03-20 | OK
1.23 | Check OSPF configuration on EU_FW_BRU | "Show running-config" | Interface Gig0/0 - ip ospf network point-to-point | 2025-03-20 | OK
1.24 |  |  | Interface Gig0/1 - ip ospf network point-to-point | 2025-03-20 | OK
1.25 |  |  | Interface Gig0/2 - ip ospf network point-to-point | 2025-03-20 | OK
1.26 |  |  | Router ospf 10 - network 172.16.1.13 0.0.0.0 area 0 | 2025-03-20 | OK
1.27 |  |  | Router ospf 10 - network 172.16.1.17 0.0.0.0 area 0 | 2025-03-20 | OK
1.28 |  |  | Router ospf 10 - network 172.16.1.21 0.0.0.0 area 0 | 2025-03-20 | OK
1.29 | Check OSPF configuration on EU_CoreSW1 | "Show running-config" | Interface Fa0/1 - ip ospf network point-to-point | 2025-03-20 | OK
1.30 |  |  | Router ospf 10 - passive-interface Fa0/2 | 2025-03-20 | OK
1.31 |  |  | Router ospf 10 - passive-interface Fa0/3 | 2025-03-20 | OK
1.32 |  |  | Router ospf 10 - passive-interface Fa0/4 | 2025-03-20 | OK
1.33 |  |  | Router ospf 10 - passive-interface Fa0/5 | 2025-03-20 | OK
1.34 |  |  | Router ospf 10 - network 172.16.1.14 0.0.0.0 area 0 | 2025-03-20 | OK
1.35 |  |  | Router ospf 10 - network 10.3.10.3 0.0.0.0 area 0 | 2025-03-20 | OK
1.36 |  |  | Router ospf 10 - network 10.3.20.3 0.0.0.0 area 0 | 2025-03-20 | OK
1.37 |  |  | Router ospf 10 - network 10.3.100.3 0.0.0.0 area 0 | 2025-03-20 | OK
1.38 |  |  | Router ospf 10 - network 10.3.200.3 0.0.0.0 area 0 | 2025-03-20 | OK
1.39 | Check OSPF configuration on EU_CoreSW2 | "Show running-config" | Interface Fa0/1 - ip ospf network point-to-point | 2025-03-20 | OK
1.40 |  |  | Router ospf 10 - passive-interface Fa0/2 | 2025-03-20 | OK
1.41 |  |  | Router ospf 10 - passive-interface Fa0/3 | 2025-03-20 | OK
1.42 |  |  | Router ospf 10 - passive-interface Fa0/4 | 2025-03-20 | OK
1.43 |  |  | Router ospf 10 - passive-interface Fa0/5 | 2025-03-20 | OK
1.44 |  |  | Router ospf 10 - network 172.16.1.18 0.0.0.0 area 0 | 2025-03-20 | OK
1.45 |  |  | Router ospf 10 - network 10.3.10.4 0.0.0.0 area 0 | 2025-03-20 | OK
1.46 |  |  | Router ospf 10 - network 10.3.20.4 0.0.0.0 area 0 | 2025-03-20 | OK
1.47 |  |  | Router ospf 10 - network 10.3.100.4 0.0.0.0 area 0 | 2025-03-20 | OK
1.48 |  |  | Router ospf 10 - network 10.3.200.4 0.0.0.0 area 0 | 2025-03-20 | OK
2. OSPF NEIGHBOR RELATIONSHIPS
2.1 | Check OSPF neighbor for US_FW_NY | "show ip ospf neighbor" | Neighbor with EU_FW_BRU - Address 172.16.1.21 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/0
2.2 |  |  | Neighbor with US_Roas_NY - Address 172.16.1.2 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/1
2.3 |  |  | Neighbor with US_Roas_CHI - Address 172.16.1.6 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/2
2.4 | Check OSPF neighbor for US_Roas_NY | "show ip ospf neighbor" | Neighbor with US_FW_NY - Address 172.16.1.1 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/2
2.5 |  |  | Neighbor with US_Roas_CHI - Address 172.16.1.9 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/1
2.6 | Check OSPF neighbor for US_Roas_CHI | "show ip ospf neighbor" | Neighbor with US_FW_NY - Address 172.16.1.5 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/2
2.7 |  |  | Neighbor with US_Roas_NY - Address 172.16.1.10 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/1
2.8 | Check OSPF neighbor for EU_FW_BRU | "show ip ospf neighbor" | Neighbor with US_FW_NY - Address 172.16.1.22 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/0
2.9 |  |  | Neighbor with EU_CoreSW1 - Address 172.16.1.14 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/1
2.10 |  |  | Neighbor with EU_CoreSW2 - Address 172.16.1.18 / State: FULL | 2025-03-20 | OK |  |  | On interface Gig0/2
2.11 | Check OSPF neighbor for EU_CoreSW1 | "show ip ospf neighbor" | Neighbor with EU_FW_BRU - Address 172.16.1.13 / State: FULL | 2025-03-20 | OK |  |  | On interface Fa0/1
2.12 |  |  | Neighbor with VLAN10 - Address 10.3.10.4 / State: FULL/DR | 2025-03-20 | OK |  |  | VLAN10
2.13 |  |  | Neighbor with VLAN20 - Address 10.3.20.4 / State: FULL/DR | 2025-03-20 | OK |  |  | VLAN20
2.14 |  |  | Neighbor with VLAN100 - Address 10.3.100.4 / State: FULL/DR | 2025-03-20 | OK |  |  | VLAN100
2.15 |  |  | Neighbor with VLAN200 - Address 10.3.200.4 / State: FULL/DR | 2025-03-20 | OK |  |  | VLAN200
2.16 | Check OSPF neighbor for EU_CoreSW2 | "show ip ospf neighbor" | Neighbor with EU_FW_BRU - Address 172.16.1.17 / State: FULL | 2025-03-20 | OK |  |  | On interface Fa0/1
2.17 |  |  | Neighbor with VLAN10 - Address 10.3.10.3 / State: FULL/BDR | 2025-03-20 | OK |  |  | VLAN10
2.18 |  |  | Neighbor with VLAN20 - Address 10.3.20.3 / State: FULL/BDR | 2025-03-20 | OK |  |  | VLAN20
2.19 |  |  | Neighbor with VLAN100 - Address 10.3.100.3 / State: FULL/BDR | 2025-03-20 | OK |  |  | VLAN100
2.20 |  |  | Neighbor with VLAN200 - Address 10.3.200.3 / State: FULL/BDR | 2025-03-20 | OK |  |  | VLAN200
3. OSPF ROUTES
3.1 | Check OSPF routes for US_FW_NY | "show ip route ospf" | All connected subnets marked with "O" (OSPF) | 2025-03-20 | OK
3.2 | Check OSPF routes for US_Roas-CHI | "show ip route ospf" | All connected subnets marked with "O" (OSPF) | 2025-03-20 | OK
3.3 | Check OSPF routes for US_Roas-NY | "show ip route ospf" | All connected subnets marked with "O" (OSPF) | 2025-03-20 | OK
3.4 | Check OSPF routes for EU_FW_BRU | "show ip route ospf" | All connected subnets marked with "O" (OSPF) | 2025-03-20 | OK
3.5 | Check OSPF routes for EU_CoreSW1 | "show ip route ospf" | All connected subnets marked with "O" (OSPF) | 2025-03-20 | OK
3.6 | Check OSPF routes for EU_CoreSW1 | "show ip route ospf" | All connected subnets marked with "O" (OSPF)
4. CHECK CONNECTIVITY
4.1 | Test connectivity between CHI-PC01 and BRU-PC02 | ping from 10.2.10.10 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK
4.2 | Test connectivity between NY-PC01 and BRU-PC02 | ping from 10.1.10.10 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK
4.3 | Test connectivity between CHI-PC01 and EU_FW_BRU | ping from 10.2.10.10 to 172.16.1.21 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK
4.4 | Test connectivity between NY-PC01 and EU_FW_BRU | ping from 10.1.10.10 to 172.16.1.21 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK
4.5 | Test connectivity between BRU-PC01 and US_FW_NY | ping from 10.3.10.10 to 172.16.1.22 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK
4.6 | Test connectivity between BRU-PC02 and US_FW_NY | ping from 10.3.10.11 to 172.16.1.22 | Ping statistics: 100% reply - 0% loss | 2025-03-20 | OK