## Test Plan
TEST # | CATEGORY | TEST CRITERIA | EXPECTED RESULT | TEST DATE | OK / NOK | RE-TEST DATE | OK / NOK | NOTES
1. Local Connectivity
1.1 | Check BXL-RTR-1 link health | Gi0/0: ping 10.0.0.2 | Ping statistics: 100% reply - 0% loss | 2022-09-18 | OK
1.2 |  | Se0/0/1: ping 172.16.255.250 | Ping statistics: 100% reply - 0% loss | 2022-09-18 | OK
1.3 |  | Se0/0/0: ping 172.16.255.246 | Ping statistics: 100% reply - 0% loss | 2022-09-18 | OK
1.9 | Check BXL-RTR-1 routing table | show ip route | 10.1.1.0/24 | 2022-09-18 | OK
1.10 |  |  | 10.1.2.0/24 | 2022-09-18 | OK
1.11 |  |  | 10.1.3.0/24 | 2022-09-18 | NOK |  |  | Investigate why this route is missing
1.12 |  |  |  | DD/MM/YYYY
1.17 |  |  |  | DD/MM/YYYY
1.18 |  |  |  | DD/MM/YYYY
1.19 |  |  |  | DD/MM/YYYY
1.20 |  |  |  | DD/MM/YYYY
1.21 |  |  |  | DD/MM/YYYY
1.22 |  |  |  | DD/MM/YYYY
1.23 |  |  |  | DD/MM/YYYY
1.24 |  |  |  | DD/MM/YYYY
1.25 |  |  |  | DD/MM/YYYY
1.26 |  |  |  | DD/MM/YYYY
1.27 |  |  |  | DD/MM/YYYY
1.28 |  |  |  | DD/MM/YYYY
1.29 |  |  |  | DD/MM/YYYY
1.30 |  |  |  | DD/MM/YYYY
2. Routing Tables
2.1 |  |  |  | DD/MM/YYYY
2.2 |  |  |  | DD/MM/YYYY
2.3 |  |  |  | DD/MM/YYYY
2.4 |  |  |  | DD/MM/YYYY
2.5 |  |  |  | DD/MM/YYYY
3. Remote Connectivity
3.1 |  |  |  | DD/MM/YYYY
3.2 |  |  |  | DD/MM/YYYY
3.3 |  |  |  | DD/MM/YYYY
3.4 |  |  |  | DD/MM/YYYY
3.5 |  |  |  | DD/MM/YYYY
4.
4.1 |  |  |  | DD/MM/YYYY
4.2 |  |  |  | DD/MM/YYYY
4.3 |  |  |  | DD/MM/YYYY
4.4 |  |  |  | DD/MM/YYYY
4.5 |  |  |  | DD/MM/YYYY
5.
5.1 |  |  |  | DD/MM/YYYY
5.2 |  |  |  | DD/MM/YYYY
5.3 |  |  |  | DD/MM/YYYY
5.4 |  |  |  | DD/MM/YYYY
5.5 |  |  |  | DD/MM/YYYY
5.6 |  |  |  | DD/MM/YYYY
5.7 |  |  |  | DD/MM/YYYY
5.8 |  |  |  | DD/MM/YYYY
5.9 |  |  |  | DD/MM/YYYY
5.10 |  |  |  | DD/MM/YYYY
5.11 |  |  |  | DD/MM/YYYY
5.12 |  |  |  | DD/MM/YYYY
5.13 |  |  |  | DD/MM/YYYY
5.14 |  |  |  | DD/MM/YYYY
5.15 |  |  |  | DD/MM/YYYY
5.16 |  |  |  | DD/MM/YYYY
5.17 |  |  |  | DD/MM/YYYY
5.18 |  |  |  | DD/MM/YYYY
5.19 |  |  |  | DD/MM/YYYY
6.
6.1 |  |  |  | DD/MM/YYYY
6.2 |  |  |  | DD/MM/YYYY
6.3 |  |  |  | DD/MM/YYYY
6.4 |  |  |  | DD/MM/YYYY
6.5 |  |  |  | DD/MM/YYYY
6.6 |  |  |  | DD/MM/YYYY
6.7 |  |  |  | DD/MM/YYYY
6.8 |  |  |  | DD/MM/YYYY
6.9 |  |  |  | DD/MM/YYYY
6.10 |  |  |  | DD/MM/YYYY
6.11 |  |  |  | DD/MM/YYYY
6.12 |  |  |  | DD/MM/YYYY
6.13 |  |  |  | DD/MM/YYYY
6.14 |  |  |  | DD/MM/YYYY
6.15 |  |  |  | DD/MM/YYYY
6.16 |  |  |  | DD/MM/YYYY
6.17 |  |  |  | DD/MM/YYYY
6.18 |  |  |  | DD/MM/YYYY
6.19 |  |  |  | DD/MM/YYYY
7.
7.1 |  |  |  | DD/MM/YYYY
7.2 |  |  |  | DD/MM/YYYY
7.3 |  |  |  | DD/MM/YYYY

## Fase 2
TEST # | CATEGORY | TEST CRITERIA | RESULT | TEST DATE | OK / NOK | RE-TEST DATE | OK / NOK | NOTES
1. Local Connectivity
1.1 | Check US_Roas_CHI link health | Gi0/0.10: ping 10.2.10.1 | Ping statistics: 100% reply - 0% loss | 2/20/2025 | OK
1.2 |  | Gi0/0.20: ping 10.2.20.1 | Ping statistics: 100% reply - 0% loss | 2/20/2025 | OK
1.3 |  | Gi0/0.100: ping 10.2.100.1 | Ping statistics: 100% reply - 0% loss | 2/20/2025 | OK
1.4 |  | Gi0/0.200: ping 10.2.200.1 | Ping statistics: 100% reply - 0% loss | 2/20/2025 | OK
1.5 | Check US_Roas_NY link health | Gi0/0.10: ping 10.1.10.1 | Ping statistics: 100% reply - 0% loss | 2/20/2025 | OK
1.6 |  | Gi0/0.20: ping 10.1.20.1 | Ping statistics: 100% reply - 0% loss | 2/20/2025 | OK
1.7 |  | Gi0/0.100: ping 10.1.100.1 | Ping statistics: 100% reply - 0% loss | 2/20/2025 | OK
1.8 |  | Gi0/0.200: ping 10.1.200.1 | Ping statistics: 100% reply - 0% loss | 2/20/2025 | OK
1.9 | Test connectivity between CHI and NY PCs | ping from 10.2.10.10 to 10.1.10.10 | Ping statistics: 100% reply - 0% loss | 2/20/2025 | OK
1.10
2. Routing Tables
2.1 | Check static routes for US_Roas_CHI | "show ip route" | Static route for 10.1.0.0/16 via 172.16.1.10 | 2/20/2025 | OK
2.2 | Check static routes for US_Roas_NY | "show ip route" | Static route for 10.2.0.0/16 via 172.16.1.9 | 2/20/2025 | OK
2.3
3. Local Connectivity
3.1 | Locally connect to US_Roas_CHI | Connect laptop to device with console cable | able to connect via Putty | 2/20/2025 | OK
3.2 | Locally connect to US_Roas_NY | Connect laptop to device with console cable | able to connect via Putty | 2/20/2025 | OK
3.3 | Locally connect to US_AccessSW_CHI | Connect laptop to device with console cable | able to connect via Putty | 2/20/2025 | OK
3.4 | Locally connect to US_AccessSW_NY | Connect laptop to device with console cable | able to connect via Putty | 2/20/2025 | OK
3.5
4. VLAN Configuation
4.1 | Check VLAN config on US_AccessSW_CHI | "show vlan brief" | VLANs 10,20,100 and 200 in overview | 2/20/2025 | OK
4.2 | Check VLAN config on US_AccessSW_NY | "show vlan brief" | VLANs 10,20,100 and 200 in overview | 2/20/2025 | OK
4.3 | Check trunking on US_AccessSW_CHI | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed | 2/20/2025 | OK
4.4 | Check trunking on US_AccessSW_NY | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed | 2/20/2025 | OK
4.5 | Check subinterfaces on US_Roas_CHI | "show ip interface brief" | Subinterfaces for VLANs 10,20,100,200 are configures | 2/20/2025 | OK
4.6 | Check subinterfaces on US_Roas_NY | "show ip interface brief" | Subinterfaces for VLANs 10,20,100,200 are configures | 2/20/2025 | OK
4.7
5. Device and connection security
5.1 | VTY lines secured | "show running config" | password set and login required | 2/20/2025 | OK
5.2 | Unused ports disabled | "show interface status" | unused ports "disabled" | 2/20/2025 | OK
5.3 | Username and password set | Connect laptop to device with console cable | Prompt for username and password | 2/20/2025 | OK
5.4
6. SSH Testing between devices
6.1 | US_Access_SW_CHI → US_Roas_CHI | ssh -l admin 10.2.100.1 | US_AccessSW_CHI#ssh -l admin 10.2.100.1 Password: US_Roas_CHI> | 2/25/2025 | OK
6.2 | US_Roas_CHI → US_Roas_NY | ssh -l admin 10.1.100.1 | US_Roas_CHI#ssh -l admin 10.1.100.1 Password: US_Roas_NY> | 2/25/2025 | OK
6.3 | US_Roas_NY → US_AccessSW_NY | ssh -l admin 10.1.100.10 | US_Roas_NY#ssh -l admin 10.1.100.10 Password: Authorised Access Only! US_AccessSW_NY> | 2/25/2025 | OK
6.4 | AND THE OTHER WAY ROUND
7.
7.1
7.2
7.3

## Fase 3
TEST # | CATEGORY | TEST CRITERIA | RESULT | TEST DATE | OK / NOK | RE-TEST DATE | OK / NOK | NOTES
1. Local Connectivity
1.1 | Check EU_CoreSW1 link health | VLAN10_SVI: ping 10.3.10.3 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.2 |  | VLAN20_SVI: ping 10.3.20.3 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.3 |  | VLAN100_SVI: ping 10.3.100.3 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.4 |  | VLAN200_SVI: ping 10.3.200.3 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.5 | Check EU_CoreSW2 link health | VLAN10_SVI: ping 10.3.10.4 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.6 |  | VLAN20_SVI: ping 10.3.20.4 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.7 |  | VLAN100_SVI: ping 10.3.100.4 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.8 |  | VLAN200_SVI: ping 10.3.200.4 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.9 | Check EU_CoreSW - HSRP link healt | VLAN10: ping 10.3.10.5 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.10 |  | VLAN20: ping 10.3.20.5 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.11 |  | VLAN100: ping 10.3.100.5 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.12 |  | VLAN200: ping 10.3.200.5 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.13 | Check EU_AccessSW1 link health | ping 10.3.100.12 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.14 | Check EU_AccessSW2 link health | ping 10.3.100.13 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.15 | Test connectivity between BRU-PC01 and BRU-PC02 | ping from 10.3.10.10 to 10.3.10.11 | Ping statistics: 100% reply - 0% loss | 2025-03-05 | OK
1.16
2. Routing Tables
2.1 | Check static routes for EU_CoreSW1 | "show ip route" | All VLAN networks + subnet "connected" | 2025-03-05 | OK |  |  | All VLAN subnets are "connected" (C)
2.2 | Check static routes for EU_CoreSW2 | "show ip route" | All VLAN networks + subnet "connected" | 2025-03-05 | OK |  |  | All VLAN subnets are "connected" (C)
2.3
3. Local Connectivity
3.1 | Locally connect to EU_CoreSW1 | Connect laptop to device with console cable | able to connect via Putty | 2025-03-05 | OK
3.2 | Locally connect to EU_CoreSW2 | Connect laptop to device with console cable | able to connect via Putty | 2025-03-05 | OK
3.3 | Locally connect to EU_AccessSW1 | Connect laptop to device with console cable | able to connect via Putty | 2025-03-05 | OK
3.4 | Locally connect to EU_AccessSW2 | Connect laptop to device with console cable | able to connect via Putty | 2025-03-05 | OK
3.5
4. VLAN Configuation
4.1 | Check VLAN config on EU_AccessSW1 | "show vlan brief" | VLANs 10,20,100 and 200 + names in overview | 2025-03-05 | OK |  |  | VLANs defined
4.2 | Check VLAN config on EU_AccessSW2 | "show vlan brief" | VLANs 10,20,100 and 200 + names in overview | 2025-03-05 | OK |  |  | VLANs defined
4.3 | Check VLAN config on EU_CoreSW1 | "show vlan brief" | VLANs 10,20,100 and 200 + names in overview | 2025-03-05 | OK |  |  | VLANs defined
4.4 | Check VLAN config on EU_CoreSW2 | "show vlan brief" | VLANs 10,20,100 and 200 + names in overview | 2025-03-05 | OK |  |  | VLANs defined
4.5 | Check trunking on EU_AccessSW1 | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed on trunk interfaces | 2025-03-05 | OK |  |  | Allowed on Fa0/1, Fa0/2
4.6 | Check trunking on EU_AccessSW2 | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed on trunk interfaces | 2025-03-05 | OK |  |  | Allowed on Fa0/1, Fa0/2
4.7 | Check trunking on EU_CoreSW1 | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed on trunk interfaces | 2025-03-05 | OK |  |  | Allowed on Po1, Fa0/4, Fa0/5
4.8 | Check trunking on EU_CoreSW2 | "show interfaces trunk" | VLANs 10,20,100 and 200 are allowed on trunk interfaces | 2025-03-05 | OK |  |  | Allowed on Po1, Fa0/4, Fa0/5
4.9 | Check subinterfaces on EU_CoreSW1 | "show ip interface brief" | Subinterfaces for VLANs 10,20,100,200 are configures | 2025-03-05 | OK |  |  | SVIs defined
4.10 | Check subinterfaces on EU_CoreSW2 | "show ip interface brief" | Subinterfaces for VLANs 10,20,100,200 are configures | 2025-03-05 | OK |  |  | SVIs defined
4.11
5. Device and connection security
5.1 | VTY lines secured on EU_CoreSW1 | "show running-config" | password set and login required | 2025-03-05 | OK |  |  | CLI prompts credentials
5.2 | VTY lines secured on EU_CoreSW2 | "show running-config" | password set and login required | 2025-03-05 | OK |  |  | CLI prompts credentials
5.3 | VTY lines secured on EU_AccessSW1 | "show running-config" | password set and login required | 2025-03-05 | OK |  |  | CLI prompts credentials
5.4 | VTY lines secured on EU_AccessSW2 | "show running-config" | password set and login required | 2025-03-05 | OK |  |  | CLI prompts credentials
5.5 | Unused ports disabled on EU_CoreSW1 | "show interface status" | unused ports "disabled" | 2025-03-05 | OK
5.6 | Unused ports disabled on EU_CoreSW2 | "show interface status" | unused ports "disabled" | 2025-03-05 | OK
5.7 | Unused ports disabled on EU_AccessSW1 | "show interface status" | unused ports "disabled" | 2025-03-05 | OK
5.8 | Unused ports disabled on EU_AccessSW2 | "show interface status" | unused ports "disabled" | 2025-03-05 | OK
5.9 | Username and password set on EU_CoreSW1 | Connect to CLI (or via SSH) | Prompt for username and password | 2025-03-05 | OK
5.10 | Username and password set on EU_CoreSW2 | Connect to CLI (or via SSH) | Prompt for username and password | 2025-03-05 | OK
5.11 | Username and password set on EU_AccessSW1 | Connect to CLI (or via SSH) | Prompt for username and password | 2025-03-05 | OK
5.12 | Username and password set on EU_AccessSW2 | Connect to CLI (or via SSH) | Prompt for username and password | 2025-03-05 | OK
5.13 | Passwords encrypted in config files for EU_CoreSW1 | "show running-config" | Passwords encrypted + "service password encryption" | 2025-03-05 | OK
5.14 | Passwords encrypted in config files for EU_CoreSW2 | "show running-config" | Passwords encrypted + "service password encryption" | 2025-03-05 | OK
5.15 | Passwords encrypted in config files for EU_AccessSw1 | "show running-config" | Passwords encrypted + "service password encryption" | 2025-03-05 | OK
5.16 | Passwords encrypted in config files for EU_AccessSw2 | "show running-config" | Passwords encrypted + "service password encryption" | 2025-03-05 | OK
5.17
6. SSH Configuration
6.1 | EU_AccessSW1 → EU_AccessSW2 | ssh -l admin 10.3.100.13 | able to connect via via SSH, password prompted and access granted | 2025-03-05 | OK
6.2 | EU_CoreSW1 → EU_CoreSW2.vlan10 | ssh -l admin 10.3.10.4 | able to connect via via SSH, password prompted and access granted | 2025-03-05 | OK
6.3 | EU_AccessSW2 → EU_CoreSW1.vlan20 | ssh -l admin 10.3.20.3 | able to connect via via SSH, password prompted and access granted | 2025-03-05 | OK
6.4 | EU_CoreSW2 → EU_AccessSW1 | ssh -l admin 10.3.100.12 | able to connect via via SSH, password prompted and access granted | 2025-03-05 | OK
6.5
7. Spanning Tree Protocol
7.1 | Rapid-PVST enabled on EU_CoreSW1 | "show running-config" | "spanning-tree mode rapid-pvst" | 2025-03-05 | OK |  |  | Priority 0 - root bridge
7.2 | Rapid-PVST enabled on EU_CoreSW2 | "show running-config" | "spanning-tree mode rapid-pvst" | 2025-03-05 | OK |  |  | Priority 4096 - secondary root bridge
7.3 | Rapid-PVST enabled on EU_AccessSW1 | "show running-config" | "spanning-tree mode rapid-pvst" | 2025-03-05 | OK
7.4 | Rapid-PVST enabled on EU_AccessSW2 | "show running-config" | "spanning-tree mode rapid-pvst" | 2025-03-05 | OK
7.5 | Ensure path changes when link is broken | Disable link between EU_CoreSW1 and EU_AccessSW2 | Packet from BRU-PC01 to BRU-PC02 takes different route | 2025-03-05 | OK |  |  | Normal route: BRU-PC01 - EU_AccessSW1 - EU_CoreSW1 - EU_AccessSW2 - BRU-PC02 New route: BRU-PC01 - EU_AccessSW1 - EU_CoreSW1 - EU_CoreSW2 - EU_AccessSW2 - BRU-PC02
7.6 | BPDU Guard enabled on EU_CoreSW1 | "show running-config" | "spanning-tree portfast bpduguard default" | 2025-03-05 | OK
7.7 | BPDU Guard enabled on EU_CoreSW2 | "show running-config" | "spanning-tree portfast bpduguard default" | 2025-03-05 | OK
7.8 | BPDU Guard enabled on EU_AccessSW1 | "show running-config" | "spanning-tree portfast bpduguard default" | 2025-03-05 | OK
7.9 | BPDU Guard enabled on EU_AccessSW2 | "show running-config" | "spanning-tree portfast bpduguard default" | 2025-03-05 | OK
7.10
8. Etherchannel
8.1 | Etherchannel enabled on EU_CoreSW1 | "show running-config" | Interface Portchannel1 defined + interfaces Fa0/2 + Fa0/3 part of Po1 | 2025-03-05 | OK
8.2 | Etherchannel enabled on EU_CoreSW1 | "show running-config" | Interface Portchannel1 defined + interfaces Fa0/2 + Fa0/3 part of Po1 | 2025-03-05 | OK
8.3 | Etherchannel enabled on EU_CoreSW2 | "show etherchannel summary" | Po1 details + interfaces Fa0/2 + Fa0/3 in port-channel | 2025-03-05 | OK
8.4 | Etherchannel enabled on EU_CoreSW2 | "show etherchannel summary" | Po1 details + interfaces Fa0/2 + Fa0/3 in port-channel | 2025-03-05 | OK
8.5
9. Hot Standby Routing Protocol (HSRP)
9.1 | HSRP enabled on EU_CoreSW1 | "show standby" | "state is active" for all VLANs | 2025-03-05 | OK
9.2 | HSRP enabled on EU_CoreSW2 | "show standby" | "state is standby" for all VLANs | 2025-03-05 | OK
9.3